## Slide 1
INTERNAL TEAM PROPOSAL
AI Guardrails
One reusable guardrail policy, applied consistently across every LLM gateway a team already runs — hosted, managed, or in the customer's own account.
Derived from solution-docs/ (L1 AGREEMENTS · CONSTRAINTS · DECISIONS) · Status: proposal for internal review · 2026-07-24 Effort and duration figures in section 5 are planning estimates authored for this deck — they are NOT part of the source-of-truth register.

## Slide 2
AGENDA
1
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
What we are asking you to review
Five sections. Sections 3–5 are the ones that need a decision.
01
Capabilities
· 37 cataloged capabilities
· 17 core (Phases 1–2)
· 20 committed later-phase
· 13 explicit exclusions
02
Use cases & modes
· 3 deployment modes (A/B/C)
· 7 actor-driven use cases
· Mode A is the front door
· B and C are graduation paths
03
Developer integration
· One evaluation contract
· Connector · SDK · raw HTTP
· One companion deck per mode
· Copy-paste examples
04
Delivery plan
· Five phases, M1–M5
· Nine-criterion validation gate at M2
· Sequencing fixed; dates are new
05
Effort estimation
· Full team roster, 9 roles
· ~545 person-weeks / ~21,800 h
· Cost/hr fields left open for finance
→
Decision asked for
· Approve Phase 1–2 execution
· Name the two pilot LiteLLM teams
· Supply blended rates to close the estimate
Notes: Frame it: sections 1-3 are 'what we are building and how you plug in'. Sections 4-5 are the ask. Everything except section 5 traces to solution-docs; section 5 numbers are ours and are explicitly labelled as such.

## Slide 3
CONTEXT
2
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
What AI Guardrails is
A hosted policy and evaluation service that attaches to a gateway you already run.
▪ The consumer keeps their gateway, their model provider and their data path.
▪ The platform hosts policy storage, evaluation, and the audited decision.
▪ A policy is defined once — checks, thresholds, actions, failure behavior — and bound to a workload at a specific immutable version.
▪ LiteLLM is the first connector, Bedrock Guardrails the first engine. Neither is the product boundary: the contract is vendor-independent by design.
▪ Security sets the floor (mandatory policies); application teams may strengthen it, never weaken it.
THE SIX-ENTITY DOMAIN MODEL (AGR-017)
Tenant
an organization or team
Workload
an app, assistant, agent or gateway
Policy
versioned checks + actions
Binding
workload ↔ policy version + mode
Evaluation
a request to inspect content
Decision
allow · block · redact · log_only
CAVEAT
Mode A is never a private-data or data-local model. Evaluated content reaches the hosted Evaluation API regardless of who runs the gateway (AGR-009). Residency requirements route to Mode C.
Source: solution-docs/20-product/SERVING-MODEL.md §1 · README §1 · AGREEMENTS AGR-003/004/017

## Slide 4
01
Capabilities
37 cataloged capabilities, split by delivery status — plus the 13 things this product deliberately will not become.
3

## Slide 5
CAPABILITIES
4
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
The capability model in one picture
Everything a consumer touches rides over one Evaluation API.
CONTROL PLANE
· Tenants & workloads
· Policies & versions
· Bindings & rollouts
· Promotion / rollback
· Dashboards
GUARDRAILS RUNTIME
· Evaluation API
· Policy resolver
· Decision engine
· Evaluator adapters
· Audit producer
EVALUATION ENGINES
· Bedrock Guardrails
· Deterministic org rules
· Sensitive-data (PII)
· Schema validators
· (future engines)
INTEGRATION CLIENTS
· LiteLLM connector
· Python SDK
· TypeScript SDK
· Raw HTTP API
· Guarded Gateway
Parity rule: a connector or SDK may never add evaluation semantics the API does not itself expose. That is what keeps a policy identical across every integration path (AGR-005, AGR-006).
Source: 50-architecture/INTEGRATION-ARCHITECTURE.md §2 · 20-product/SERVING-MODEL.md §4

## Slide 6
CAPABILITIES
5
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Core capabilities — Phases 1–2 (available at GA)
17 capabilities, CAP-001 … CAP-017. These are what the Phase 1–2 release gate is judged against.
Area | Capabilities | What it gives a team
Policy governance | CAP-001 | Versioned, immutable, rollback-able policies
Workload & binding | CAP-002, 003 | Register a workload; bind it to a policy version + mode
Evaluation | CAP-004, 005 | Input (pre-model) and output (post-model) evaluation
Connectors & APIs | CAP-006 … 008 | LiteLLM pre/post-call connector + generic HTTP API
Evaluation engines | CAP-009 … 011 | Bedrock adapter, deterministic rules, basic PII handling
Decisions & audit | CAP-012 … 015 | Normalized decisions, observe/enforce, latency, audit metadata
Deployment | CAP-016, 017 | Hosted runtime + architected path to customer-managed
Availability | CAP-035 (avail.) | Multi-region availability, tenant pinned to one region
Source: 20-product/CAPABILITIES.md — Core capabilities, Phases 1–2
Notes: Do not overclaim: per-tenant residency ENFORCEMENT is later-phase; only availability is core.

## Slide 7
CAPABILITIES
6
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Committed later-phase capabilities — Phases 3–5
20 capabilities, CAP-018 … CAP-037. Estimated and committed, not built during Phases 1–2, not available today.
Theme | Capabilities | Phase
Extended evaluation scope | Retrieval content, indirect prompt injection, streaming output, tool-call validation, MCP authorization, memory-write, groundedness, automated reasoning, multilingual packs | Mostly 5
Extended governance | Human approval workflows, policy signing, policy inheritance, customer evaluator plugins, policy marketplace | 3–5
Deployment & commercial | Dedicated hosted runtimes, air-gapped install, commercial metering, per-tenant residency enforcement, multi-region active-active, per-category decision metrics | 3–5
CAVEAT
Phase assignment is a scope decision, not an editorial one. Nothing in this table may be pulled forward into Phases 1–2 without a recorded change to the L1 registers (DEC-008, AGR-020).
Source: 20-product/CAPABILITIES.md — Later-phase capabilities · DECISIONS DEC-008, DEC-018–020

## Slide 8
CAPABILITIES
7
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
What this product deliberately is not
13 product-category exclusions. They are not a backlog — re-entering any of them needs a new agreement.
✕ General-purpose LLM gateway replacement
✕ Complete AI governance platform
✕ Model training or fine-tuning
✕ Proprietary prompt-injection model
✕ Proprietary moderation model
✕ Complete DLP platform
✕ End-user authentication
✕ Application business authorization
✕ Fully autonomous agent governance
✕ Organization-wide AWS enforcement
✕ Cross-cloud deployment
✕ Full compliance certification
✕ General MCP security platform
NON-NEGOTIABLE FRAMING
Two honesty caveats we carry into every conversation: (1) a cooperatively installed connector can always be disabled or misconfigured — 'mandatory' in Mode A is a governance guarantee, not a physical one (AGR-018); (2) a guardrail decision is never an authorization decision (AGR-010).
Source: 20-product/CAPABILITIES.md · 70-governance/CLAIMS-REGISTER.md

## Slide 9
02
Use cases — the three modes
Mode A is the front door. Modes B and C exist to answer two specific objections, not to compete for the first conversation.
8

## Slide 10
MODES
9
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Three deployment modes at a glance
One logical evaluation contract across all three. Only the network location of the Evaluation API changes.
MODE A · PHASES 1–2 · FRONT DOOR
Remote Evaluation
· You keep your own gateway (LiteLLM) or call the API directly
· Connector calls the hosted Evaluation API pre- and post-call
· Smallest footprint for both sides
· Content DOES reach the hosted API
MODE B · PHASE 3
Guarded Gateway
· Answers: "we have no gateway"
· Provider-run, OpenAI-compatible endpoint
· Provider owns credentials, routing, retries, quotas
· Largest provider operational + compliance scope
MODE C · PHASE 4
Customer-Managed Runtime
· Answers: "content can't leave our account"
· Runtime deploys into the customer's AWS account
· Local policy cache; runs without control plane
· Raw content stays in-account by default
Concern | Mode A | Mode B | Mode C
Gateway owned by | Consuming team | Provider | Consuming team
Evaluation API runs | Hosted (provider) | Hosted, inside the gateway | Customer AWS account
Contract shape | Unchanged | Unchanged | Unchanged
Source: 20-product/SERVING-MODEL.md §2/§6 · 50-architecture/INTEGRATION-ARCHITECTURE.md §8

## Slide 11
MODES
10
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Who owns what, per mode
Adopting a mode is a commitment on both sides. This table is the commitment.
Ownership item | Mode A — Remote Evaluation | Mode B — Guarded Gateway | Mode C — Customer-Managed
Gateway infra & availability | Consuming team | Platform operations | Consuming team
Model credentials & routing | Consuming team | Platform operations | Consuming team
Retry / fallback / model cost | Consuming team | Platform operations | Consuming team
Policy execution & decisions | AI Guardrails team + Platform ops | AI Guardrails team (in gateway) | AI Guardrails team (shipped runtime)
Audit storage | Platform operations | Platform operations | Consuming team (local)
Runtime upgrades | Provider applies | Provider applies | Consuming team, unless managed support
Policy approval, retention, audit rules | Security & governance | Security & governance | Security & governance
Source: 60-delivery/TEAM-AND-OWNERSHIP.md §4

## Slide 12
USE CASES
11
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Seven use cases, and when each becomes real
UC-001, 005, 006 and 007 together are the Phase 1–2 validation demonstration — all four, or the gate does not pass.
ID | Use case | Mode | Status
UC-001 | Two independent LiteLLM instances share one central policy | A | Phases 1–2 · core demo
UC-002 | Onboard in observe mode, then promote to enforce | Any | Phases 1–2
UC-003 | Regulated workload keeps content inside its own account | C | Target state — Phase 4
UC-004 | A team with no gateway uses the Guarded Gateway | B | Target state — Phase 3
UC-005 | Central policy upgrade and immediate rollback | Any | Phases 1–2 · core demo
UC-006 | Disable raw-content persistence for a sensitive workload | Any | Phases 1–2 · core demo
UC-007 | Configured failure behavior on evaluation timeout | Any | Phases 1–2 · core demo
Source: 20-product/USE-CASES.md — use case index
Notes: If asked 'what proves this works?': UC-001 is the falsifiable hypothesis — two organizationally independent LiteLLM instances, same policy version, consistent normalized decisions, no shared model-provider credentials. One instance tested twice does not count.

## Slide 13
USE CASES
12
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
The canonical onboarding flow
Seven steps. This is what 'import a policy' means — and what it never means.
1
Register workload
2
Select policy
3
Generate manifest
4
Install connector
5
Run in observe
6
Review results
7
Enable enforcement
Enforcement progression on a binding: Disabled → Observe → Warn → Redact → Block (every promotion is explicit and audited; a new binding never defaults to Block)
WHAT IMPORT IS NOT
Import never requires: copying your LiteLLM database · transferring model-provider credentials · exposing gateway admin endpoints · replacing your model routing · granting the provider admin access to your gateway (AGR-019).
Source: 60-delivery/IMPLEMENTATION-STRATEGY.md §7 · AGREEMENTS AGR-011, AGR-019

## Slide 14
03
Developer integration
One contract, three clients. Detailed, copy-paste integration walkthroughs ship as one companion deck per mode.
13

## Slide 15
INTEGRATION
14
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
One contract, three clients
A policy behaves identically whether it is reached through the connector, an SDK, or a raw HTTP call.
PAVED PATH
LiteLLM connector
· Pre-call + post-call callbacks
· Config-only install, no app code change
· Enforces block / redact in the request path
· Propagates the correlation id
DIRECT
Python / TypeScript SDK
· For apps not fronted by a supported gateway
· Request construction + timeout handling
· Same decision object as the connector
· No added evaluation semantics
ALWAYS OPEN
Raw HTTP Evaluation API
· Any stack with an authenticated HTTP client
· The real product surface
· No consumer is locked out for lacking an SDK
· Conformance-testable
The evaluation request carries | The decision returns
tenant id · workload id · stage (input¦output) · content payload · correlation id · optional policy hint | action (allow¦block¦redact¦log_only) · allowed · reason codes · policy name+version · evaluator metadata · transformed content · correlation id · audit id · latency
Companion decks — one per mode: Mode-A-Remote-Evaluation.pptx · Mode-B-Guarded-Gateway.pptx · Mode-C-Customer-Managed-Runtime.pptx
Source: 50-architecture/INTEGRATION-ARCHITECTURE.md §3, §5 · 20-product/SERVING-MODEL.md §4

## Slide 16
INTEGRATION
15
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
The pre-call / post-call pattern
The same sequence in all three modes — only the destination of the Evaluation API changes.
evaluation flow
Application ──► Gateway / SDK ──► Evaluation API (stage=input, correlation_id=X)
◄── decision: allow | block | redact | log_only
block ──► safe rejection returned to the caller, model never invoked
redact ──► model invoked with the transformed content from the decision
allow ──► model invoked with the original content
Model ──► Gateway / SDK ──► Evaluation API (stage=output, correlation_id=X)
◄── decision: allow | block | redact | log_only
block ──► safe fallback response returned instead of the raw model output
redact ──► transformed response returned
allow ──► original response returned
Timeout / detector down / policy unresolvable ──► the workload's CONFIGURED failure
behavior runs. There is no undocumented fallback (AGR-012).
CORRELATION
Two evaluations share one correlation id, so the input decision, the model call, the output decision and both audit records join into a single traceable request.
Source: 50-architecture/INTEGRATION-ARCHITECTURE.md §4.1, §4.4, §4.6

## Slide 17
04
Delivery plan
Five phases, five milestones, one hard validation gate. Sequencing is agreed; the calendar in this section is our proposal.
16

## Slide 18
DELIVERY
17
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Five phases — sequencing is fixed by agreement
Each phase's deliverables must be completed and validated before the next phase's scope is committed (AGR-020).
PHASE 1
Integration proof
· Evaluation contract
· Policy format
· Bedrock adapter
· LiteLLM connector
· Observe mode
· Basic auditing
· Internal deployment
PHASE 2
Multi-team platform
· Tenant + workload registry
· Policy bindings
· IAM auth
· Quotas
· Promotion + rollback
· Service monitoring
· Basic admin workflow
PHASE 3
Guarded gateway
· Managed gateway
· Model-provider config
· Per-tenant routing
· Cost + rate controls
· Managed credentials
· Residency enforcement
· Active-active
PHASE 4
Customer-managed runtime
· Runtime container
· Helm chart
· ECS template
· IaC module
· Local policy cache
· Async policy sync
· Customer telemetry
PHASE 5
Advanced agent protection
· Retrieval evaluation
· Tool-call validation
· Tool-result evaluation
· Memory-write control
· Human approvals
· MCP integration
· Delegation limits
Phases 1–2 = the core platform (Mode A). Phase 3 = Mode B. Phase 4 = Mode C. Phase 5 is committed and estimated, but sequenced last and never resourced inside Phases 1–4.
Source: 20-product/PRODUCT-ROADMAP.md · 60-delivery/MILESTONES.md

## Slide 19
DELIVERY
18
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
The gate: nine criteria, all together, at M2
Phases 1–2 are not validated when the components exist. They are validated when all nine of these hold simultaneously.
# | Criterion | First demonstrable
MVP-01 | Two separate LiteLLM instances consume the same policy | M1
MVP-02 | Neither instance shares model-provider credentials with the platform | M1
MVP-03 | Both receive consistent normalized decisions | M1
MVP-04 | One workload runs in observe mode | M1
MVP-05 | Another workload runs in enforce mode | M1
MVP-06 | A policy can be upgraded and rolled back | M2 ← the gate closes here
MVP-07 | Raw content persistence can be disabled | M1
MVP-08 | Evaluation failures follow a configured failure policy | M1
MVP-09 | Runtime can be packaged for customer-managed use, contract unchanged | M1 (shipped at M4)
THE ONE ASK THAT BLOCKS US
Hard dependency on you: two GENUINELY INDEPENDENT LiteLLM deployments — different teams, different instances, different provider credentials. One deployment tested twice does not satisfy MVP-01. We need those two teams named before Phase 1 starts.
Source: 60-delivery/MILESTONES.md §8 · 10-charter/SUCCESS-CRITERIA.md §1.2–1.3

## Slide 20
DELIVERY
19
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Proposed schedule and gates
Sequencing comes from AGR-020. The week counts below are this deck's planning estimate and are not in the source-of-truth set.
Milestone | Phase | Proposed duration | Cumulative | Exit gate
M1 | Integration proof | 10 weeks | wk 10 | 8 of 9 MVP criteria verified
M2 | Multi-team platform | 10 weeks | wk 20 | All 9 criteria — Phases 1–2 VALIDATED
M3 | Guarded gateway | 14 weeks | wk 34 | ≥1 workload live end-to-end on Mode B
M4 | Customer-managed runtime | 12 weeks | wk 46 | ≥1 deployment validated in a customer account
M5 | Advanced agent protection | 16 weeks | wk 62 | All Phase 5 stages behind the same adapter pattern
≈ 62 working weeks end to end if phases run strictly back to back (~14 calendar months, before holidays and gate-review time). M3 and M4 are independent extensions of the M2 baseline and could overlap if staffed separately.
RECOMMENDATION
Funding decision granularity: approve M1+M2 now; treat M3 and M4 as separate, later-gated decisions. That is the framing the executive brief already uses.
Source: Durations: planning estimate authored for this deck. Phase content: 60-delivery/MILESTONES.md

## Slide 21
DELIVERY
20
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
What gates us — dependencies and sequencing risks
Dependency / risk | Why it gates delivery | Mitigation in the plan
Two independent LiteLLM instances | MVP-01 cannot be exercised without them | Name and commit both pilot teams before M1 starts
Bedrock Guardrails availability | First evaluation engine; adapter cannot be validated without it | All vendor shape absorbed at the adapter boundary
Two-account AWS model provisioned | Nothing deploys without it | Minimal model is sufficient; no speculative 3rd account
Security & governance engagement | No policy can be authored or promoted without approval | Engage from Phase 1, not at go-live
Connector bypass | A cooperative connector can be removed or misconfigured | Disclosed, never marketed as a hard boundary
False confidence | Teams may read 'evaluation passed' as 'AI is secure' | LiteLLM first, generic API second, against a stable contract
Product over-expansion | Phase 3–5 scope creeping into Phases 1–2 | Phase assignment changes require an L1 register change
Source: 60-delivery/IMPLEMENTATION-STRATEGY.md §6, §9 · 70-governance/RISK-REGISTER.md

## Slide 22
05
Effort estimation
A full delivery team, sized per phase, in person-weeks and hours. Rate and cost columns are deliberately left open.
21

## Slide 23
EFFORT
22
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
The team this needs
Nine roles. Consuming teams participate but are not a program headcount line.
Role | Owns | Peak FTE
Product lead / PM | Scope discipline, onboarding experience, success metrics, register hygiene | 0.5
Tech lead / architect | Evaluation contract, policy schema, domain model, ADRs, review gate | 1.0
Backend / platform engineers ×3 | Runtime, policy resolver, decision engine, evaluator adapters, control plane | 3.0
Connector / SDK engineer | LiteLLM pre/post-call connector, Python + TypeScript SDKs, conformance suite | 1.0
Cloud / DevOps engineer | AWS footprint, IaC, CI/CD, container + Helm + ECS packaging (Phase 4) | 1.0–2.0
Security engineer | IAM, KMS, tenant isolation, content-exposure review, threat modelling | 0.3–1.0
QA / test automation | Contract conformance, the nine-criterion demo harness, regression, load | 1.0
Technical writer / DevRel | Integration docs, runbooks, per-mode developer guides | 0.3–0.5
SRE / platform operations | Monitoring, capacity, incident response — scales up from Phase 2 | 0.5–1.0
Source: Roles derived from 30-executive/INVESTMENT-SUMMARY.md §3 and 60-delivery/TEAM-AND-OWNERSHIP.md. FTE figures are this deck's estimate — the source documents state headcount as TBD.

## Slide 24
EFFORT
23
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Effort by phase — person-weeks and hours
Person-weeks = Σ(role FTE × phase weeks). Hours = person-weeks × 40. Cost columns are for finance to fill.
Phase | Weeks | Team FTE | Person-weeks | Hours | Blended $/hr | Phase cost
1 — Integration proof | 10 | 8.1 | 81 | 3,240 | ________ | ________
2 — Multi-team platform | 10 | 8.5 | 85 | 3,400 | ________ | ________
Core subtotal (Phases 1–2) | 20 | — | 166 | 6,640 | ________ | ________
3 — Guarded gateway | 14 | 9.5 | 133 | 5,320 | ________ | ________
4 — Customer-managed runtime | 12 | 8.5 | 102 | 4,080 | ________ | ________
5 — Advanced agent protection | 16 | 9.0 | 144 | 5,760 | ________ | ________
TOTAL — full five-phase scope | 62 | — | 545 | 21,800 | ________ | ________
Add a risk contingency on top of the hours above before quoting: +20% recommended for Phases 1–2 (new contract, new domain), +25–30% for Phases 3–5 (larger operational surface, unresolved open questions).
NOT IN THE ESTIMATE
Excluded from these hours: AWS run cost (usage-driven, workload volume is unknown — ASM-001); Bedrock Guardrails invocation cost; consuming-team effort to install connectors and review observe-mode findings; compliance certification; any commercial/billing platform.
Notes: If challenged on the numbers: they are a bottom-up FTE×duration model built for this deck. The solution docs deliberately say TBD because no figures exist in the seed. These are ours, labelled as ours, and are meant to be argued with.

## Slide 25
EFFORT
24
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
Cost worksheet — fill the rates, the totals compute
Per-role rates let procurement model a blend rather than a single average.
Role | Total person-weeks | Total hours | Rate $/hr | Total cost
Product lead / PM | 31.5 | 1,260 | ________ | ________
Tech lead / architect | 62.0 | 2,480 | ________ | ________
Backend / platform engineers (3) | 174.0 | 6,960 | ________ | ________
Connector / SDK engineer | 36.0 | 1,440 | ________ | ________
Cloud / DevOps engineer | 81.0 | 3,240 | ________ | ________
Security engineer | 37.0 | 1,480 | ________ | ________
QA / test automation | 62.0 | 2,480 | ________ | ________
Technical writer / DevRel | 29.0 | 1,160 | ________ | ________
SRE / platform operations | 33.0 | 1,320 | ________ | ________
TOTAL | 545.5 | 21,820 | — | ________
Plus, as separate lines finance should add: AWS run cost (TBD, usage-driven) · Bedrock Guardrails invocations (TBD) · contingency % · post-GA run-and-maintain
Source: Role totals are the per-phase FTE model rolled up; they sum to the 545 person-weeks on the previous slide (rounding aside). All rates and costs intentionally blank.

## Slide 26
EFFORT
25
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
What the estimate assumes
State these out loud before anyone quotes the number.
▪ Phases run strictly sequentially, with a validation gate between each.
▪ A 40-hour person-week; no overtime absorbed into the model.
▪ The team is dedicated, not time-sliced across other programs.
▪ Bedrock Guardrails is available in the target account and region from day one.
▪ The two-account AWS model is provisioned before Phase 1 build starts.
▪ Two pilot consuming teams are committed and available for the M2 demonstration.
▪ Open questions that could move the number:
  – OQ-001 — which enforcement posture the first external customers require
  – OQ-009 — the trigger for a third AWS account
  – OQ-014 — objective go/no-go criteria for observe → enforce
  – OQ-012 — policy signing and inheritance design
  – Unset SLA, latency and size limits (CON-015, CON-016)
WHERE THESE NUMBERS LIVE
Governance note: solution-docs/ states headcount, duration and budget as TBD on purpose — no figure exists in the seed. Everything numeric in this section was authored for this deck. If leadership adopts these numbers, they belong in ASSUMPTIONS.md, not in this file.

## Slide 27
CLOSE
26
AI Guardrails — internal proposal · derived from solution-docs/ · not for external distribution
What we need from this room
DECISION 1
Approve Phases 1–2
· 20 weeks, 166 person-weeks, 6,640 hours
· Gate: all nine MVP criteria at M2
· M3 and M4 stay separate, later decisions
DECISION 2
Name the two pilot teams
· Two organizationally independent LiteLLM instances
· Different provider credentials
· This is a hard blocker on MVP-01
DECISION 3
Supply the rates
· Per-role or blended $/hr
· Plus a contingency percentage
· Then the cost worksheet closes itself
▪ Read next: the three per-mode integration decks — Mode A (Remote Evaluation), Mode B (Guarded Gateway), Mode C (Customer-Managed Runtime).
▪ Read before saying anything externally: 70-governance/CLAIMS-REGISTER.md.
▪ Everything non-numeric in this deck traces to solution-docs/. Where the two ever disagree, solution-docs wins and this deck gets corrected.