## Read me
AI Guardrails — delivery model
Milestones, dependencies and gates are transcribed from solution-docs. The effort model laid over them is an assumption, not an estimate.
How to use it
1. Open Assumptions. | The only sheet with typed-in numbers, and every one is a placeholder chosen to make the model run. Replace them.
2. Check the AI-assistance factors. | They assume everyone here delivers with an agentic coding tool. Zero them for the unassisted model.
3. Set a day rate per role. | Leave them empty and every cost column stays empty rather than showing a misleading zero.
4. Argue with the sizes and role splits. | Both are judgements, editable on Work items, reasoned in the generator.
5. Stress it. | Sensitivity moves contingency and assistance together. Pivot data is the flat grain — build your own pivots off it.
How to read a cell
INPUT | An assumption you own. Nothing in the source documentation supplies this value — edit it.
DERIVED | Read from solution-docs at build time. Editing it here changes nothing upstream and is overwritten on the next build.
COMPUTED | A formula over the other two. Never type over it.
What this workbook does not say
No schedule | Milestone order is dependency sequencing. No dates, quarters or durations exist upstream and none are invented here.
Nothing is built | Every work item is planned work. There is no percent-complete column because there is nothing to report against.
The effort model is yours | Not an estimate the programme has produced. That estimation is owed by delivery and product leads and has not been supplied.
Phases 3–5 are not funded | They are estimated because the feature set is defined across all five phases — not because the work may start before the gate.
AI assistance is this workbook's own assumption | Stated in no source document. It reduces effort per role, never elapsed time — the external dependencies are approval-bound.
Where the content comes from
Sheet | Source
Work items | MILESTONES.md §3–§7 completion criteria, document order
Roadmap | MILESTONES.md §2–§7; AGR-020 five-phase delivery
Dependencies | DEPENDENCIES.md §2 register and §3 detail
Release gates | RELEASE-CRITERIA.md gate tables
Roles | TEAM-AND-OWNERSHIP.md §1 four ownership groups
Sizes and role splits | Nowhere — assumed here. See Assumptions.
AI-assistance factors | Nowhere, and in no other document — assumed here.
Every chart and rollup | Formulas over the two rows above.

## Dashboard
Dashboard
Every figure is a formula over Assumptions and Work items. Change an assumption and every chart here moves with it.
TOTAL DAYS, AFTER AI ASSIST |  | TOTAL DAYS, BEFORE AI ASSIST |  | DAYS THE ASSIST ASSUMPTION REMOVES | DAYS BEHIND THE PHASE 1–2 GATE
The headline number. It is a model output, not an estimate. |  | Set every assistance factor to zero and the headline becomes this. |  | Removed by an assumption this workbook makes on its own authority. | M1 and M2 only. The rest is estimated, and must not be resourced yet.
Where the effort sits
Milestone | Days after AI assist
M1
M2
M3
M4
M5
What the AI-assistance assumption buys
Role | Before assist | After assist
AIG
OPS
SEC
CONS
How the role mix shifts across the milestones
Milestone | AIG | OPS | SEC | CONS
M1
M2
M3
M4
M5
The shape of the work
Size | Work items | Days after AI assist
S
M
L
XL
Effort by workstream
Workstream | Work items | Days after AI assist
Contract
Evaluation
Connector
Runtime
Audit
Observability
Infrastructure
Validation
Packaging
Control plane
Security
Gateway
Operability
Governance
Integration

## Assumptions
Assumptions — the only sheet you edit
Everything else in this workbook is either transcribed from the documentation or computed from what is here.
The person-day values below are PLACEHOLDERS chosen so the model runs. No effort estimate exists upstream. Replace them before quoting any total.
Size | Label | Person-days (unassisted) | What it means
S | Small | 5 | A bounded change inside one component.
M | Medium | 15 | One component, built and tested.
L | Large | 40 | A subsystem, or a contract surface with published semantics.
XL | Extra large | 80 | A subsystem of a kind this platform has not built before.
Role | Name | Day rate | Mandate
AIG | AI Guardrails team |  | Architecture, policy schemas, evaluation contract, runtime, connectors, integrations, compatibility, telemetry, documentation, deployment artifacts
OPS | Platform operations |  | The provider's own hosted infrastructure day to day — deployment, monitoring, capacity, networking, incident response
SEC | Security and governance |  | Organization-level policy requirements; approves policy, risk, retention and audit rules
CONS | Consuming teams |  | Applications and workloads bound to policies, including any internal gateway they operate themselves
Contingency | Applied to every work item | 0% | One uplift across the whole model. Zero by default — inventing a contingency figure on your behalf would defeat the point of this sheet. Sensitivity shows the range.
Role | AI assist | Effort reduction | Why this figure and not another
AIG | AI Guardrails team | 30% | Contracts, policy schemas, evaluator adapters, connectors, runtime, deployment artifacts, tests and documentation — greenfield, well-specified, code-shaped work, and by far the largest share of this model. This is where an agentic coding tool earns most of what it is going to earn.
OPS | Platform operations | 15% | Infrastructure modules, dashboards and runbooks compress. Account provisioning, managed-engine access in the target Regions, capacity and incident response are approval-bound and wall-clock, and do not.
SEC | Security and governance | 10% | Drafting policy requirements and assembling review evidence compresses. Judgement, approval and accountability do not — and the criteria that would satisfy security sign-off are themselves undefined today.
CONS | Consuming teams | 10% | Onboarding and connector installation compress a little. The validation demonstration is gated by a second team's availability and willingness, which no tool shortens.
Planning assumptions, not measurements. Published results range from large gains to none, and one controlled trial found experienced engineers slower. Zero these four cells and the workbook recovers the unassisted model.
Day rates ship empty on purpose: with no rate set, every cost column stays blank rather than computing a zero that could pass for a real figure.

## Work items
Work items
One row per milestone completion criterion, in document order. Size and role split are yours to edit; everything shaded blue is a formula. Filter from the header row.
ID | Milestone | Workstream | Work item | Size | Base days | Days incl. cont. (unassisted) | AIG share | OPS share | SEC share | CONS share | Share Σ | AIG days | OPS days | SEC days | CONS days | Days after AI assist
WI-001 | M1 | Contract | Evaluation contract defined and published — request structure, decision structure, reason codes, policy-version semantics, expressed independently of any gateway or vendor | L |  |  | 100% | 0% | 0% | 0%
WI-002 | M1 | Contract | Guardrail policy format defined as a versioned, vendor-independent schema | L |  |  | 100% | 0% | 0% | 0%
WI-003 | M1 | Evaluation | Amazon Bedrock Guardrails adapter, normalizing vendor responses into the platform's own decision structure before they reach any policy or connector | L |  |  | 100% | 0% | 0% | 0%
WI-004 | M1 | Evaluation | Basic deterministic evaluator behind the same evaluator-adapter pattern | M |  |  | 100% | 0% | 0% | 0%
WI-005 | M1 | Connector | LiteLLM pre-call connector, invoking input evaluation before model invocation | L |  |  | 100% | 0% | 0% | 0%
WI-006 | M1 | Connector | LiteLLM post-call connector, invoking output evaluation and applying safe output fallbacks | L |  |  | 100% | 0% | 0% | 0%
WI-007 | M1 | Connector | Conformance: connectors invoke the Evaluation API only — no policy logic, thresholds or detection rules embedded | S |  |  | 80% | 0% | 20% | 0%
WI-008 | M1 | Runtime | Observe mode implemented and made the default state for a new policy binding | M |  |  | 100% | 0% | 0% | 0%
WI-009 | M1 | Audit | Basic auditing: decision metadata logged for every evaluation — tenant, workload, policy version, stage, decision, reason codes, evaluator versions, timestamp, correlation identifier, retention flag | L |  |  | 100% | 0% | 0% | 0%
WI-010 | M1 | Observability | Evaluation latency measured per evaluation at P50, P95 and P99 | M |  |  | 60% | 40% | 0% | 0%
WI-011 | M1 | Infrastructure | Runtime deployed internally within the minimal account model — one non-production and one production account | L |  |  | 30% | 70% | 0% | 0%
WI-012 | M1 | Infrastructure | TLS on all runtime communication between connectors, the Evaluation API and evaluation engines | S |  |  | 20% | 60% | 20% | 0%
WI-013 | M1 | Validation | Two independently deployed instances resolve decisions from the same published policy version, neither transmitting provider credentials — MVP-01, MVP-02, MVP-03 | M |  |  | 40% | 20% | 0% | 40%
WI-014 | M1 | Validation | One of the two workloads runs in observe mode — MVP-04 | S |  |  | 40% | 0% | 0% | 60%
WI-015 | M1 | Validation | The other workload runs in enforce mode and a violation triggers the corresponding action on the request path — MVP-05 | S |  |  | 30% | 0% | 20% | 50%
WI-016 | M1 | Validation | Raw prompt and response persistence can be disabled and is verified absent from storage, caches and logs, with decision metadata still persisted — MVP-07 | M |  |  | 30% | 20% | 50% | 0%
WI-017 | M1 | Validation | A forced detector or Evaluation API failure executes the configured failure behavior exactly as configured, captured in the audit record — MVP-08 | M |  |  | 70% | 30% | 0% | 0%
WI-018 | M1 | Packaging | Runtime validated as buildable and deployable as a standalone artifact suitable for a future customer-managed environment, connector contract unchanged — MVP-09 (architectural) | M |  |  | 70% | 30% | 0% | 0%
WI-019 | M2 | Control plane | Tenant and workload registry exposing both domain entities as first-class, queryable records | L |  |  | 100% | 0% | 0% | 0%
WI-020 | M2 | Control plane | Policy bindings associating a workload with a specific policy version and an explicit enforcement-mode selection | L |  |  | 100% | 0% | 0% | 0%
WI-021 | M2 | Security | IAM-based authentication for platform consumers using least-privilege, short-lived credentials | M |  |  | 50% | 30% | 20% | 0%
WI-022 | M2 | Security | Per-tenant workload identities issued and enforced; none shared across tenants | M |  |  | 60% | 0% | 40% | 0%
WI-023 | M2 | Control plane | Quotas implemented and enforced per tenant and per workload | M |  |  | 70% | 30% | 0% | 0%
WI-024 | M2 | Control plane | Policy promotion: a new immutable version published and bound through a controlled, auditable step | L |  |  | 100% | 0% | 0% | 0%
WI-025 | M2 | Control plane | Policy rollback: a binding reverted to a prior immutable version with prior behavior restored, both transitions in audit metadata | M |  |  | 100% | 0% | 0% | 0%
WI-026 | M2 | Runtime | Promotion between ladder states is an explicit, auditable action — never an implicit side effect of another change | M |  |  | 80% | 0% | 20% | 0%
WI-027 | M2 | Observability | Service-level monitoring covering evaluation latency, timeout rate, decision distribution and policy-cache hit rate | L |  |  | 40% | 60% | 0% | 0%
WI-028 | M2 | Control plane | Basic administration workflow for tenant, workload and binding management — a minimal management API and version-controlled configuration are acceptable at this milestone | M |  |  | 100% | 0% | 0% | 0%
WI-029 | M2 | Validation | Two internal teams have independently registered a workload, bound it to the same shared policy version, and operate under distinct identities and distinct enforcement modes | M |  |  | 30% | 0% | 20% | 50%
WI-030 | M2 | Validation | A published policy version is upgraded for one workload and rolled back, both behaviors verified and both transitions in the audit trail — MVP-06 | S |  |  | 50% | 0% | 20% | 30%
WI-031 | M3 | Gateway | A managed gateway operated end to end by the provider | XL |  |  | 50% | 50% | 0% | 0%
WI-032 | M3 | Gateway | Model-provider configuration implemented and operated by the provider, not the consuming team, for gateway traffic | M |  |  | 30% | 70% | 0% | 0%
WI-033 | M3 | Gateway | Per-tenant routing directing each tenant's inference traffic to the correct model configuration | L |  |  | 60% | 40% | 0% | 0%
WI-034 | M3 | Gateway | Cost and rate controls covering rate limits and usage quotas for the managed path | L |  |  | 60% | 40% | 0% | 0%
WI-035 | M3 | Security | Managed credential custody: the provider holds provider credentials for gateway traffic and the consuming team supplies none | M |  |  | 20% | 50% | 30% | 0%
WI-036 | M3 | Operability | A unified availability objective spanning model routing and guardrail evaluation is defined and documented — the objective, not a specific figure | S |  |  | 40% | 60% | 0% | 0%
WI-037 | M3 | Validation | At least one workload onboarded and operating end to end through the gateway with input guardrails, routing, invocation, output guardrails and reporting on one request path | M |  |  | 40% | 30% | 0% | 30%
WI-038 | M3 | Governance | Content-exposure documentation for the gateway mode published, separating operational ownership from data exposure | S |  |  | 50% | 0% | 50% | 0%
WI-039 | M3 | Contract | The evaluation contract, decision structure, reason codes and policy-version semantics verified unchanged for gateway traffic | S |  |  | 100% | 0% | 0% | 0%
WI-040 | M4 | Packaging | Runtime container image published as a supported deployment artifact | M |  |  | 70% | 30% | 0% | 0%
WI-041 | M4 | Packaging | Helm chart published for Kubernetes-based customer deployment | M |  |  | 60% | 40% | 0% | 0%
WI-042 | M4 | Packaging | ECS deployment template published | M |  |  | 60% | 40% | 0% | 0%
WI-043 | M4 | Packaging | Infrastructure module published for provisioning the customer-managed runtime | L |  |  | 40% | 60% | 0% | 0%
WI-044 | M4 | Runtime | Local policy cache enabling execution without a synchronous control-plane connection | L |  |  | 100% | 0% | 0% | 0%
WI-045 | M4 | Runtime | Policy synchronization implemented as an asynchronous process that never blocks the evaluation path | L |  |  | 100% | 0% | 0% | 0%
WI-046 | M4 | Runtime | Degraded-mode behavior for a stale local cache defined as an explicit part of the workload's failure behavior | M |  |  | 80% | 0% | 20% | 0%
WI-047 | M4 | Runtime | Customer-controlled telemetry spanning the full range down to a fully supported no-telemetry configuration | L |  |  | 70% | 0% | 30% | 0%
WI-048 | M4 | Validation | Raw content verified never to leave the customer-managed runtime unless the customer has explicitly configured that transmission | M |  |  | 40% | 0% | 60% | 0%
WI-049 | M4 | Control plane | Upgrade compatibility checks validating that a runtime upgrade stays compatible with the policy versions bound to that deployment | M |  |  | 100% | 0% | 0% | 0%
WI-050 | M4 | Validation | One customer-managed deployment validated end to end inside a customer-controlled account: local evaluation, cache behavior during a simulated outage, telemetry configuration, upgrade check | L |  |  | 40% | 20% | 0% | 40%
WI-051 | M4 | Contract | Connector invocation contract verified unchanged between hosted and customer-managed deployments — MVP-09 in shipped form | S |  |  | 100% | 0% | 0% | 0%
WI-052 | M5 | Evaluation | Retrieval-content evaluation available as an evaluator behind the existing adapter pattern, without redesigning the evaluation contract | L |  |  | 100% | 0% | 0% | 0%
WI-053 | M5 | Evaluation | Indirect prompt-injection detection available as a new evaluator behind the same adapter pattern | XL |  |  | 100% | 0% | 0% | 0%
WI-054 | M5 | Evaluation | Tool-call validation using the tool_call evaluation stage | L |  |  | 100% | 0% | 0% | 0%
WI-055 | M5 | Evaluation | Tool-result evaluation using the tool_result evaluation stage | L |  |  | 100% | 0% | 0% | 0%
WI-056 | M5 | Evaluation | Memory-write controls using the memory_write evaluation stage, fitted to the existing Evaluation and Decision entities | L |  |  | 100% | 0% | 0% | 0%
WI-057 | M5 | Control plane | Human approval workflows for the require_approval decision action, which is reserved in the schema but has no owning workflow before this milestone | XL |  |  | 70% | 0% | 30% | 0%
WI-058 | M5 | Evaluation | Agent delegation restrictions | L |  |  | 100% | 0% | 0% | 0%
WI-059 | M5 | Integration | MCP integration scoped narrowly to the platform's own tool-call evaluation, explicitly distinguished from a general-purpose MCP security platform | L |  |  | 80% | 0% | 20% | 0%
WI-060 | M5 | Integration | Advanced authorization integration, without redefining a guardrail decision as a business-authorization decision | L |  |  | 70% | 0% | 30% | 0%
Total

## Effort by role
Effort by role
Every cell is a formula over Work items and Assumptions. Milestone columns are net of each role's AI-assistance reduction; the two columns after the total show what that reduction removed.
Role | Name | M1 | M2 | M3 | M4 | M5 | Total days | Before assist | Removed | AI assist | Day rate | Cost
AIG | AI Guardrails team
OPS | Platform operations
SEC | Security and governance
CONS | Consuming teams
Total
Cost stays blank until a day rate is set on Assumptions. With only some rates set, the total covers only those roles.

## Effort by milestone
Effort by milestone
The same model rolled up the other way, net of AI assistance. Milestone order is dependency sequencing — it carries no dates and implies no schedule.
Milestone | Name | Phase | AIG days | OPS days | SEC days | CONS days | Total days | Work items | Cost
M1 | Integration proof | Phase 1
M2 | Internal multi-team platform | Phase 2
M3 | Guarded gateway | Phase 3
M4 | Customer-managed runtime | Phase 4
M5 | Advanced agent protection | Phase 5
Total
M3–M5 lie beyond the Phase 1–2 validation gate. Their totals appear because the feature set is estimated across all five phases, not because the work may start.

## Effort by workstream
Effort by workstream
Rolled up on the dimension the milestones cut across. Document order, not size order — a ranking that reshuffled on every edit would imply a stability this model does not have.
Workstream | Work items | Days after assist | Before assist | Removed | AIG days | OPS days | SEC days | CONS days
Contract
Evaluation
Connector
Runtime
Audit
Observability
Infrastructure
Validation
Packaging
Control plane
Security
Gateway
Operability
Governance
Integration
Total

## Sensitivity
Sensitivity
Total person-days as the two knobs move. The contingency column here is local to this sheet and does not change Assumptions; the assistance multiplier scales every role's factor at once.
Base days, no contingency, no assistance | AIG | OPS | SEC | CONS
Per role
Contingency | No assistance | Half the assumed | The assumed factors
0%
5%
10%
15%
20%
25%
The spread across this grid is wider than any difference the model's role splits produce. Argue about these two numbers first.

## Pivot data
Pivot data
Every work item, once per role. Insert → PivotTable over this sheet and slice it any way the rollups do not. Rows with a zero share are kept so the grain stays rectangular.
Work item | Milestone | Phase | Workstream | Size | Role | Share | Days before assist | Days after assist | Description
WI-001 | M1 | Phase 1 | Contract | L | AIG |  |  |  | Evaluation contract defined and published — request structure, decision structure, reason codes, policy-version semantics, expressed independently of any gateway or vendor
WI-001 | M1 | Phase 1 | Contract | L | OPS |  |  |  | Evaluation contract defined and published — request structure, decision structure, reason codes, policy-version semantics, expressed independently of any gateway or vendor
WI-001 | M1 | Phase 1 | Contract | L | SEC |  |  |  | Evaluation contract defined and published — request structure, decision structure, reason codes, policy-version semantics, expressed independently of any gateway or vendor
WI-001 | M1 | Phase 1 | Contract | L | CONS |  |  |  | Evaluation contract defined and published — request structure, decision structure, reason codes, policy-version semantics, expressed independently of any gateway or vendor
WI-002 | M1 | Phase 1 | Contract | L | AIG |  |  |  | Guardrail policy format defined as a versioned, vendor-independent schema
WI-002 | M1 | Phase 1 | Contract | L | OPS |  |  |  | Guardrail policy format defined as a versioned, vendor-independent schema
WI-002 | M1 | Phase 1 | Contract | L | SEC |  |  |  | Guardrail policy format defined as a versioned, vendor-independent schema
WI-002 | M1 | Phase 1 | Contract | L | CONS |  |  |  | Guardrail policy format defined as a versioned, vendor-independent schema
WI-003 | M1 | Phase 1 | Evaluation | L | AIG |  |  |  | Amazon Bedrock Guardrails adapter, normalizing vendor responses into the platform's own decision structure before they reach any policy or connector
WI-003 | M1 | Phase 1 | Evaluation | L | OPS |  |  |  | Amazon Bedrock Guardrails adapter, normalizing vendor responses into the platform's own decision structure before they reach any policy or connector
WI-003 | M1 | Phase 1 | Evaluation | L | SEC |  |  |  | Amazon Bedrock Guardrails adapter, normalizing vendor responses into the platform's own decision structure before they reach any policy or connector
WI-003 | M1 | Phase 1 | Evaluation | L | CONS |  |  |  | Amazon Bedrock Guardrails adapter, normalizing vendor responses into the platform's own decision structure before they reach any policy or connector
WI-004 | M1 | Phase 1 | Evaluation | M | AIG |  |  |  | Basic deterministic evaluator behind the same evaluator-adapter pattern
WI-004 | M1 | Phase 1 | Evaluation | M | OPS |  |  |  | Basic deterministic evaluator behind the same evaluator-adapter pattern
WI-004 | M1 | Phase 1 | Evaluation | M | SEC |  |  |  | Basic deterministic evaluator behind the same evaluator-adapter pattern
WI-004 | M1 | Phase 1 | Evaluation | M | CONS |  |  |  | Basic deterministic evaluator behind the same evaluator-adapter pattern
WI-005 | M1 | Phase 1 | Connector | L | AIG |  |  |  | LiteLLM pre-call connector, invoking input evaluation before model invocation
WI-005 | M1 | Phase 1 | Connector | L | OPS |  |  |  | LiteLLM pre-call connector, invoking input evaluation before model invocation
WI-005 | M1 | Phase 1 | Connector | L | SEC |  |  |  | LiteLLM pre-call connector, invoking input evaluation before model invocation
WI-005 | M1 | Phase 1 | Connector | L | CONS |  |  |  | LiteLLM pre-call connector, invoking input evaluation before model invocation
WI-006 | M1 | Phase 1 | Connector | L | AIG |  |  |  | LiteLLM post-call connector, invoking output evaluation and applying safe output fallbacks
WI-006 | M1 | Phase 1 | Connector | L | OPS |  |  |  | LiteLLM post-call connector, invoking output evaluation and applying safe output fallbacks
WI-006 | M1 | Phase 1 | Connector | L | SEC |  |  |  | LiteLLM post-call connector, invoking output evaluation and applying safe output fallbacks
WI-006 | M1 | Phase 1 | Connector | L | CONS |  |  |  | LiteLLM post-call connector, invoking output evaluation and applying safe output fallbacks
WI-007 | M1 | Phase 1 | Connector | S | AIG |  |  |  | Conformance: connectors invoke the Evaluation API only — no policy logic, thresholds or detection rules embedded
WI-007 | M1 | Phase 1 | Connector | S | OPS |  |  |  | Conformance: connectors invoke the Evaluation API only — no policy logic, thresholds or detection rules embedded
WI-007 | M1 | Phase 1 | Connector | S | SEC |  |  |  | Conformance: connectors invoke the Evaluation API only — no policy logic, thresholds or detection rules embedded
WI-007 | M1 | Phase 1 | Connector | S | CONS |  |  |  | Conformance: connectors invoke the Evaluation API only — no policy logic, thresholds or detection rules embedded
WI-008 | M1 | Phase 1 | Runtime | M | AIG |  |  |  | Observe mode implemented and made the default state for a new policy binding
WI-008 | M1 | Phase 1 | Runtime | M | OPS |  |  |  | Observe mode implemented and made the default state for a new policy binding
WI-008 | M1 | Phase 1 | Runtime | M | SEC |  |  |  | Observe mode implemented and made the default state for a new policy binding
WI-008 | M1 | Phase 1 | Runtime | M | CONS |  |  |  | Observe mode implemented and made the default state for a new policy binding
WI-009 | M1 | Phase 1 | Audit | L | AIG |  |  |  | Basic auditing: decision metadata logged for every evaluation — tenant, workload, policy version, stage, decision, reason codes, evaluator versions, timestamp, correlation identifier, retention flag
WI-009 | M1 | Phase 1 | Audit | L | OPS |  |  |  | Basic auditing: decision metadata logged for every evaluation — tenant, workload, policy version, stage, decision, reason codes, evaluator versions, timestamp, correlation identifier, retention flag
WI-009 | M1 | Phase 1 | Audit | L | SEC |  |  |  | Basic auditing: decision metadata logged for every evaluation — tenant, workload, policy version, stage, decision, reason codes, evaluator versions, timestamp, correlation identifier, retention flag
WI-009 | M1 | Phase 1 | Audit | L | CONS |  |  |  | Basic auditing: decision metadata logged for every evaluation — tenant, workload, policy version, stage, decision, reason codes, evaluator versions, timestamp, correlation identifier, retention flag
WI-010 | M1 | Phase 1 | Observability | M | AIG |  |  |  | Evaluation latency measured per evaluation at P50, P95 and P99
WI-010 | M1 | Phase 1 | Observability | M | OPS |  |  |  | Evaluation latency measured per evaluation at P50, P95 and P99
WI-010 | M1 | Phase 1 | Observability | M | SEC |  |  |  | Evaluation latency measured per evaluation at P50, P95 and P99
WI-010 | M1 | Phase 1 | Observability | M | CONS |  |  |  | Evaluation latency measured per evaluation at P50, P95 and P99
WI-011 | M1 | Phase 1 | Infrastructure | L | AIG |  |  |  | Runtime deployed internally within the minimal account model — one non-production and one production account
WI-011 | M1 | Phase 1 | Infrastructure | L | OPS |  |  |  | Runtime deployed internally within the minimal account model — one non-production and one production account
WI-011 | M1 | Phase 1 | Infrastructure | L | SEC |  |  |  | Runtime deployed internally within the minimal account model — one non-production and one production account
WI-011 | M1 | Phase 1 | Infrastructure | L | CONS |  |  |  | Runtime deployed internally within the minimal account model — one non-production and one production account
WI-012 | M1 | Phase 1 | Infrastructure | S | AIG |  |  |  | TLS on all runtime communication between connectors, the Evaluation API and evaluation engines
WI-012 | M1 | Phase 1 | Infrastructure | S | OPS |  |  |  | TLS on all runtime communication between connectors, the Evaluation API and evaluation engines
WI-012 | M1 | Phase 1 | Infrastructure | S | SEC |  |  |  | TLS on all runtime communication between connectors, the Evaluation API and evaluation engines
WI-012 | M1 | Phase 1 | Infrastructure | S | CONS |  |  |  | TLS on all runtime communication between connectors, the Evaluation API and evaluation engines
WI-013 | M1 | Phase 1 | Validation | M | AIG |  |  |  | Two independently deployed instances resolve decisions from the same published policy version, neither transmitting provider credentials — MVP-01, MVP-02, MVP-03
WI-013 | M1 | Phase 1 | Validation | M | OPS |  |  |  | Two independently deployed instances resolve decisions from the same published policy version, neither transmitting provider credentials — MVP-01, MVP-02, MVP-03
WI-013 | M1 | Phase 1 | Validation | M | SEC |  |  |  | Two independently deployed instances resolve decisions from the same published policy version, neither transmitting provider credentials — MVP-01, MVP-02, MVP-03
WI-013 | M1 | Phase 1 | Validation | M | CONS |  |  |  | Two independently deployed instances resolve decisions from the same published policy version, neither transmitting provider credentials — MVP-01, MVP-02, MVP-03
WI-014 | M1 | Phase 1 | Validation | S | AIG |  |  |  | One of the two workloads runs in observe mode — MVP-04
WI-014 | M1 | Phase 1 | Validation | S | OPS |  |  |  | One of the two workloads runs in observe mode — MVP-04
WI-014 | M1 | Phase 1 | Validation | S | SEC |  |  |  | One of the two workloads runs in observe mode — MVP-04
WI-014 | M1 | Phase 1 | Validation | S | CONS |  |  |  | One of the two workloads runs in observe mode — MVP-04
WI-015 | M1 | Phase 1 | Validation | S | AIG |  |  |  | The other workload runs in enforce mode and a violation triggers the corresponding action on the request path — MVP-05
WI-015 | M1 | Phase 1 | Validation | S | OPS |  |  |  | The other workload runs in enforce mode and a violation triggers the corresponding action on the request path — MVP-05
WI-015 | M1 | Phase 1 | Validation | S | SEC |  |  |  | The other workload runs in enforce mode and a violation triggers the corresponding action on the request path — MVP-05
WI-015 | M1 | Phase 1 | Validation | S | CONS |  |  |  | The other workload runs in enforce mode and a violation triggers the corresponding action on the request path — MVP-05
WI-016 | M1 | Phase 1 | Validation | M | AIG |  |  |  | Raw prompt and response persistence can be disabled and is verified absent from storage, caches and logs, with decision metadata still persisted — MVP-07
WI-016 | M1 | Phase 1 | Validation | M | OPS |  |  |  | Raw prompt and response persistence can be disabled and is verified absent from storage, caches and logs, with decision metadata still persisted — MVP-07
WI-016 | M1 | Phase 1 | Validation | M | SEC |  |  |  | Raw prompt and response persistence can be disabled and is verified absent from storage, caches and logs, with decision metadata still persisted — MVP-07
WI-016 | M1 | Phase 1 | Validation | M | CONS |  |  |  | Raw prompt and response persistence can be disabled and is verified absent from storage, caches and logs, with decision metadata still persisted — MVP-07
WI-017 | M1 | Phase 1 | Validation | M | AIG |  |  |  | A forced detector or Evaluation API failure executes the configured failure behavior exactly as configured, captured in the audit record — MVP-08
WI-017 | M1 | Phase 1 | Validation | M | OPS |  |  |  | A forced detector or Evaluation API failure executes the configured failure behavior exactly as configured, captured in the audit record — MVP-08
WI-017 | M1 | Phase 1 | Validation | M | SEC |  |  |  | A forced detector or Evaluation API failure executes the configured failure behavior exactly as configured, captured in the audit record — MVP-08
WI-017 | M1 | Phase 1 | Validation | M | CONS |  |  |  | A forced detector or Evaluation API failure executes the configured failure behavior exactly as configured, captured in the audit record — MVP-08
WI-018 | M1 | Phase 1 | Packaging | M | AIG |  |  |  | Runtime validated as buildable and deployable as a standalone artifact suitable for a future customer-managed environment, connector contract unchanged — MVP-09 (architectural)
WI-018 | M1 | Phase 1 | Packaging | M | OPS |  |  |  | Runtime validated as buildable and deployable as a standalone artifact suitable for a future customer-managed environment, connector contract unchanged — MVP-09 (architectural)
WI-018 | M1 | Phase 1 | Packaging | M | SEC |  |  |  | Runtime validated as buildable and deployable as a standalone artifact suitable for a future customer-managed environment, connector contract unchanged — MVP-09 (architectural)
WI-018 | M1 | Phase 1 | Packaging | M | CONS |  |  |  | Runtime validated as buildable and deployable as a standalone artifact suitable for a future customer-managed environment, connector contract unchanged — MVP-09 (architectural)
WI-019 | M2 | Phase 2 | Control plane | L | AIG |  |  |  | Tenant and workload registry exposing both domain entities as first-class, queryable records
WI-019 | M2 | Phase 2 | Control plane | L | OPS |  |  |  | Tenant and workload registry exposing both domain entities as first-class, queryable records
WI-019 | M2 | Phase 2 | Control plane | L | SEC |  |  |  | Tenant and workload registry exposing both domain entities as first-class, queryable records
WI-019 | M2 | Phase 2 | Control plane | L | CONS |  |  |  | Tenant and workload registry exposing both domain entities as first-class, queryable records
WI-020 | M2 | Phase 2 | Control plane | L | AIG |  |  |  | Policy bindings associating a workload with a specific policy version and an explicit enforcement-mode selection
WI-020 | M2 | Phase 2 | Control plane | L | OPS |  |  |  | Policy bindings associating a workload with a specific policy version and an explicit enforcement-mode selection
WI-020 | M2 | Phase 2 | Control plane | L | SEC |  |  |  | Policy bindings associating a workload with a specific policy version and an explicit enforcement-mode selection
WI-020 | M2 | Phase 2 | Control plane | L | CONS |  |  |  | Policy bindings associating a workload with a specific policy version and an explicit enforcement-mode selection
WI-021 | M2 | Phase 2 | Security | M | AIG |  |  |  | IAM-based authentication for platform consumers using least-privilege, short-lived credentials
WI-021 | M2 | Phase 2 | Security | M | OPS |  |  |  | IAM-based authentication for platform consumers using least-privilege, short-lived credentials
WI-021 | M2 | Phase 2 | Security | M | SEC |  |  |  | IAM-based authentication for platform consumers using least-privilege, short-lived credentials
WI-021 | M2 | Phase 2 | Security | M | CONS |  |  |  | IAM-based authentication for platform consumers using least-privilege, short-lived credentials
WI-022 | M2 | Phase 2 | Security | M | AIG |  |  |  | Per-tenant workload identities issued and enforced; none shared across tenants
WI-022 | M2 | Phase 2 | Security | M | OPS |  |  |  | Per-tenant workload identities issued and enforced; none shared across tenants
WI-022 | M2 | Phase 2 | Security | M | SEC |  |  |  | Per-tenant workload identities issued and enforced; none shared across tenants
WI-022 | M2 | Phase 2 | Security | M | CONS |  |  |  | Per-tenant workload identities issued and enforced; none shared across tenants
WI-023 | M2 | Phase 2 | Control plane | M | AIG |  |  |  | Quotas implemented and enforced per tenant and per workload
WI-023 | M2 | Phase 2 | Control plane | M | OPS |  |  |  | Quotas implemented and enforced per tenant and per workload
WI-023 | M2 | Phase 2 | Control plane | M | SEC |  |  |  | Quotas implemented and enforced per tenant and per workload
WI-023 | M2 | Phase 2 | Control plane | M | CONS |  |  |  | Quotas implemented and enforced per tenant and per workload
WI-024 | M2 | Phase 2 | Control plane | L | AIG |  |  |  | Policy promotion: a new immutable version published and bound through a controlled, auditable step
WI-024 | M2 | Phase 2 | Control plane | L | OPS |  |  |  | Policy promotion: a new immutable version published and bound through a controlled, auditable step
WI-024 | M2 | Phase 2 | Control plane | L | SEC |  |  |  | Policy promotion: a new immutable version published and bound through a controlled, auditable step
WI-024 | M2 | Phase 2 | Control plane | L | CONS |  |  |  | Policy promotion: a new immutable version published and bound through a controlled, auditable step
WI-025 | M2 | Phase 2 | Control plane | M | AIG |  |  |  | Policy rollback: a binding reverted to a prior immutable version with prior behavior restored, both transitions in audit metadata
WI-025 | M2 | Phase 2 | Control plane | M | OPS |  |  |  | Policy rollback: a binding reverted to a prior immutable version with prior behavior restored, both transitions in audit metadata
WI-025 | M2 | Phase 2 | Control plane | M | SEC |  |  |  | Policy rollback: a binding reverted to a prior immutable version with prior behavior restored, both transitions in audit metadata
WI-025 | M2 | Phase 2 | Control plane | M | CONS |  |  |  | Policy rollback: a binding reverted to a prior immutable version with prior behavior restored, both transitions in audit metadata
WI-026 | M2 | Phase 2 | Runtime | M | AIG |  |  |  | Promotion between ladder states is an explicit, auditable action — never an implicit side effect of another change
WI-026 | M2 | Phase 2 | Runtime | M | OPS |  |  |  | Promotion between ladder states is an explicit, auditable action — never an implicit side effect of another change
WI-026 | M2 | Phase 2 | Runtime | M | SEC |  |  |  | Promotion between ladder states is an explicit, auditable action — never an implicit side effect of another change
WI-026 | M2 | Phase 2 | Runtime | M | CONS |  |  |  | Promotion between ladder states is an explicit, auditable action — never an implicit side effect of another change
WI-027 | M2 | Phase 2 | Observability | L | AIG |  |  |  | Service-level monitoring covering evaluation latency, timeout rate, decision distribution and policy-cache hit rate
WI-027 | M2 | Phase 2 | Observability | L | OPS |  |  |  | Service-level monitoring covering evaluation latency, timeout rate, decision distribution and policy-cache hit rate
WI-027 | M2 | Phase 2 | Observability | L | SEC |  |  |  | Service-level monitoring covering evaluation latency, timeout rate, decision distribution and policy-cache hit rate
WI-027 | M2 | Phase 2 | Observability | L | CONS |  |  |  | Service-level monitoring covering evaluation latency, timeout rate, decision distribution and policy-cache hit rate
WI-028 | M2 | Phase 2 | Control plane | M | AIG |  |  |  | Basic administration workflow for tenant, workload and binding management — a minimal management API and version-controlled configuration are acceptable at this milestone
WI-028 | M2 | Phase 2 | Control plane | M | OPS |  |  |  | Basic administration workflow for tenant, workload and binding management — a minimal management API and version-controlled configuration are acceptable at this milestone
WI-028 | M2 | Phase 2 | Control plane | M | SEC |  |  |  | Basic administration workflow for tenant, workload and binding management — a minimal management API and version-controlled configuration are acceptable at this milestone
WI-028 | M2 | Phase 2 | Control plane | M | CONS |  |  |  | Basic administration workflow for tenant, workload and binding management — a minimal management API and version-controlled configuration are acceptable at this milestone
WI-029 | M2 | Phase 2 | Validation | M | AIG |  |  |  | Two internal teams have independently registered a workload, bound it to the same shared policy version, and operate under distinct identities and distinct enforcement modes
WI-029 | M2 | Phase 2 | Validation | M | OPS |  |  |  | Two internal teams have independently registered a workload, bound it to the same shared policy version, and operate under distinct identities and distinct enforcement modes
WI-029 | M2 | Phase 2 | Validation | M | SEC |  |  |  | Two internal teams have independently registered a workload, bound it to the same shared policy version, and operate under distinct identities and distinct enforcement modes
WI-029 | M2 | Phase 2 | Validation | M | CONS |  |  |  | Two internal teams have independently registered a workload, bound it to the same shared policy version, and operate under distinct identities and distinct enforcement modes
WI-030 | M2 | Phase 2 | Validation | S | AIG |  |  |  | A published policy version is upgraded for one workload and rolled back, both behaviors verified and both transitions in the audit trail — MVP-06
WI-030 | M2 | Phase 2 | Validation | S | OPS |  |  |  | A published policy version is upgraded for one workload and rolled back, both behaviors verified and both transitions in the audit trail — MVP-06
WI-030 | M2 | Phase 2 | Validation | S | SEC |  |  |  | A published policy version is upgraded for one workload and rolled back, both behaviors verified and both transitions in the audit trail — MVP-06
WI-030 | M2 | Phase 2 | Validation | S | CONS |  |  |  | A published policy version is upgraded for one workload and rolled back, both behaviors verified and both transitions in the audit trail — MVP-06
WI-031 | M3 | Phase 3 | Gateway | XL | AIG |  |  |  | A managed gateway operated end to end by the provider
WI-031 | M3 | Phase 3 | Gateway | XL | OPS |  |  |  | A managed gateway operated end to end by the provider
WI-031 | M3 | Phase 3 | Gateway | XL | SEC |  |  |  | A managed gateway operated end to end by the provider
WI-031 | M3 | Phase 3 | Gateway | XL | CONS |  |  |  | A managed gateway operated end to end by the provider
WI-032 | M3 | Phase 3 | Gateway | M | AIG |  |  |  | Model-provider configuration implemented and operated by the provider, not the consuming team, for gateway traffic
WI-032 | M3 | Phase 3 | Gateway | M | OPS |  |  |  | Model-provider configuration implemented and operated by the provider, not the consuming team, for gateway traffic
WI-032 | M3 | Phase 3 | Gateway | M | SEC |  |  |  | Model-provider configuration implemented and operated by the provider, not the consuming team, for gateway traffic
WI-032 | M3 | Phase 3 | Gateway | M | CONS |  |  |  | Model-provider configuration implemented and operated by the provider, not the consuming team, for gateway traffic
WI-033 | M3 | Phase 3 | Gateway | L | AIG |  |  |  | Per-tenant routing directing each tenant's inference traffic to the correct model configuration
WI-033 | M3 | Phase 3 | Gateway | L | OPS |  |  |  | Per-tenant routing directing each tenant's inference traffic to the correct model configuration
WI-033 | M3 | Phase 3 | Gateway | L | SEC |  |  |  | Per-tenant routing directing each tenant's inference traffic to the correct model configuration
WI-033 | M3 | Phase 3 | Gateway | L | CONS |  |  |  | Per-tenant routing directing each tenant's inference traffic to the correct model configuration
WI-034 | M3 | Phase 3 | Gateway | L | AIG |  |  |  | Cost and rate controls covering rate limits and usage quotas for the managed path
WI-034 | M3 | Phase 3 | Gateway | L | OPS |  |  |  | Cost and rate controls covering rate limits and usage quotas for the managed path
WI-034 | M3 | Phase 3 | Gateway | L | SEC |  |  |  | Cost and rate controls covering rate limits and usage quotas for the managed path
WI-034 | M3 | Phase 3 | Gateway | L | CONS |  |  |  | Cost and rate controls covering rate limits and usage quotas for the managed path
WI-035 | M3 | Phase 3 | Security | M | AIG |  |  |  | Managed credential custody: the provider holds provider credentials for gateway traffic and the consuming team supplies none
WI-035 | M3 | Phase 3 | Security | M | OPS |  |  |  | Managed credential custody: the provider holds provider credentials for gateway traffic and the consuming team supplies none
WI-035 | M3 | Phase 3 | Security | M | SEC |  |  |  | Managed credential custody: the provider holds provider credentials for gateway traffic and the consuming team supplies none
WI-035 | M3 | Phase 3 | Security | M | CONS |  |  |  | Managed credential custody: the provider holds provider credentials for gateway traffic and the consuming team supplies none
WI-036 | M3 | Phase 3 | Operability | S | AIG |  |  |  | A unified availability objective spanning model routing and guardrail evaluation is defined and documented — the objective, not a specific figure
WI-036 | M3 | Phase 3 | Operability | S | OPS |  |  |  | A unified availability objective spanning model routing and guardrail evaluation is defined and documented — the objective, not a specific figure
WI-036 | M3 | Phase 3 | Operability | S | SEC |  |  |  | A unified availability objective spanning model routing and guardrail evaluation is defined and documented — the objective, not a specific figure
WI-036 | M3 | Phase 3 | Operability | S | CONS |  |  |  | A unified availability objective spanning model routing and guardrail evaluation is defined and documented — the objective, not a specific figure
WI-037 | M3 | Phase 3 | Validation | M | AIG |  |  |  | At least one workload onboarded and operating end to end through the gateway with input guardrails, routing, invocation, output guardrails and reporting on one request path
WI-037 | M3 | Phase 3 | Validation | M | OPS |  |  |  | At least one workload onboarded and operating end to end through the gateway with input guardrails, routing, invocation, output guardrails and reporting on one request path
WI-037 | M3 | Phase 3 | Validation | M | SEC |  |  |  | At least one workload onboarded and operating end to end through the gateway with input guardrails, routing, invocation, output guardrails and reporting on one request path
WI-037 | M3 | Phase 3 | Validation | M | CONS |  |  |  | At least one workload onboarded and operating end to end through the gateway with input guardrails, routing, invocation, output guardrails and reporting on one request path
WI-038 | M3 | Phase 3 | Governance | S | AIG |  |  |  | Content-exposure documentation for the gateway mode published, separating operational ownership from data exposure
WI-038 | M3 | Phase 3 | Governance | S | OPS |  |  |  | Content-exposure documentation for the gateway mode published, separating operational ownership from data exposure
WI-038 | M3 | Phase 3 | Governance | S | SEC |  |  |  | Content-exposure documentation for the gateway mode published, separating operational ownership from data exposure
WI-038 | M3 | Phase 3 | Governance | S | CONS |  |  |  | Content-exposure documentation for the gateway mode published, separating operational ownership from data exposure
WI-039 | M3 | Phase 3 | Contract | S | AIG |  |  |  | The evaluation contract, decision structure, reason codes and policy-version semantics verified unchanged for gateway traffic
WI-039 | M3 | Phase 3 | Contract | S | OPS |  |  |  | The evaluation contract, decision structure, reason codes and policy-version semantics verified unchanged for gateway traffic
WI-039 | M3 | Phase 3 | Contract | S | SEC |  |  |  | The evaluation contract, decision structure, reason codes and policy-version semantics verified unchanged for gateway traffic
WI-039 | M3 | Phase 3 | Contract | S | CONS |  |  |  | The evaluation contract, decision structure, reason codes and policy-version semantics verified unchanged for gateway traffic
WI-040 | M4 | Phase 4 | Packaging | M | AIG |  |  |  | Runtime container image published as a supported deployment artifact
WI-040 | M4 | Phase 4 | Packaging | M | OPS |  |  |  | Runtime container image published as a supported deployment artifact
WI-040 | M4 | Phase 4 | Packaging | M | SEC |  |  |  | Runtime container image published as a supported deployment artifact
WI-040 | M4 | Phase 4 | Packaging | M | CONS |  |  |  | Runtime container image published as a supported deployment artifact
WI-041 | M4 | Phase 4 | Packaging | M | AIG |  |  |  | Helm chart published for Kubernetes-based customer deployment
WI-041 | M4 | Phase 4 | Packaging | M | OPS |  |  |  | Helm chart published for Kubernetes-based customer deployment
WI-041 | M4 | Phase 4 | Packaging | M | SEC |  |  |  | Helm chart published for Kubernetes-based customer deployment
WI-041 | M4 | Phase 4 | Packaging | M | CONS |  |  |  | Helm chart published for Kubernetes-based customer deployment
WI-042 | M4 | Phase 4 | Packaging | M | AIG |  |  |  | ECS deployment template published
WI-042 | M4 | Phase 4 | Packaging | M | OPS |  |  |  | ECS deployment template published
WI-042 | M4 | Phase 4 | Packaging | M | SEC |  |  |  | ECS deployment template published
WI-042 | M4 | Phase 4 | Packaging | M | CONS |  |  |  | ECS deployment template published
WI-043 | M4 | Phase 4 | Packaging | L | AIG |  |  |  | Infrastructure module published for provisioning the customer-managed runtime
WI-043 | M4 | Phase 4 | Packaging | L | OPS |  |  |  | Infrastructure module published for provisioning the customer-managed runtime
WI-043 | M4 | Phase 4 | Packaging | L | SEC |  |  |  | Infrastructure module published for provisioning the customer-managed runtime
WI-043 | M4 | Phase 4 | Packaging | L | CONS |  |  |  | Infrastructure module published for provisioning the customer-managed runtime
WI-044 | M4 | Phase 4 | Runtime | L | AIG |  |  |  | Local policy cache enabling execution without a synchronous control-plane connection
WI-044 | M4 | Phase 4 | Runtime | L | OPS |  |  |  | Local policy cache enabling execution without a synchronous control-plane connection
WI-044 | M4 | Phase 4 | Runtime | L | SEC |  |  |  | Local policy cache enabling execution without a synchronous control-plane connection
WI-044 | M4 | Phase 4 | Runtime | L | CONS |  |  |  | Local policy cache enabling execution without a synchronous control-plane connection
WI-045 | M4 | Phase 4 | Runtime | L | AIG |  |  |  | Policy synchronization implemented as an asynchronous process that never blocks the evaluation path
WI-045 | M4 | Phase 4 | Runtime | L | OPS |  |  |  | Policy synchronization implemented as an asynchronous process that never blocks the evaluation path
WI-045 | M4 | Phase 4 | Runtime | L | SEC |  |  |  | Policy synchronization implemented as an asynchronous process that never blocks the evaluation path
WI-045 | M4 | Phase 4 | Runtime | L | CONS |  |  |  | Policy synchronization implemented as an asynchronous process that never blocks the evaluation path
WI-046 | M4 | Phase 4 | Runtime | M | AIG |  |  |  | Degraded-mode behavior for a stale local cache defined as an explicit part of the workload's failure behavior
WI-046 | M4 | Phase 4 | Runtime | M | OPS |  |  |  | Degraded-mode behavior for a stale local cache defined as an explicit part of the workload's failure behavior
WI-046 | M4 | Phase 4 | Runtime | M | SEC |  |  |  | Degraded-mode behavior for a stale local cache defined as an explicit part of the workload's failure behavior
WI-046 | M4 | Phase 4 | Runtime | M | CONS |  |  |  | Degraded-mode behavior for a stale local cache defined as an explicit part of the workload's failure behavior
WI-047 | M4 | Phase 4 | Runtime | L | AIG |  |  |  | Customer-controlled telemetry spanning the full range down to a fully supported no-telemetry configuration
WI-047 | M4 | Phase 4 | Runtime | L | OPS |  |  |  | Customer-controlled telemetry spanning the full range down to a fully supported no-telemetry configuration
WI-047 | M4 | Phase 4 | Runtime | L | SEC |  |  |  | Customer-controlled telemetry spanning the full range down to a fully supported no-telemetry configuration
WI-047 | M4 | Phase 4 | Runtime | L | CONS |  |  |  | Customer-controlled telemetry spanning the full range down to a fully supported no-telemetry configuration
WI-048 | M4 | Phase 4 | Validation | M | AIG |  |  |  | Raw content verified never to leave the customer-managed runtime unless the customer has explicitly configured that transmission
WI-048 | M4 | Phase 4 | Validation | M | OPS |  |  |  | Raw content verified never to leave the customer-managed runtime unless the customer has explicitly configured that transmission
WI-048 | M4 | Phase 4 | Validation | M | SEC |  |  |  | Raw content verified never to leave the customer-managed runtime unless the customer has explicitly configured that transmission
WI-048 | M4 | Phase 4 | Validation | M | CONS |  |  |  | Raw content verified never to leave the customer-managed runtime unless the customer has explicitly configured that transmission
WI-049 | M4 | Phase 4 | Control plane | M | AIG |  |  |  | Upgrade compatibility checks validating that a runtime upgrade stays compatible with the policy versions bound to that deployment
WI-049 | M4 | Phase 4 | Control plane | M | OPS |  |  |  | Upgrade compatibility checks validating that a runtime upgrade stays compatible with the policy versions bound to that deployment
WI-049 | M4 | Phase 4 | Control plane | M | SEC |  |  |  | Upgrade compatibility checks validating that a runtime upgrade stays compatible with the policy versions bound to that deployment
WI-049 | M4 | Phase 4 | Control plane | M | CONS |  |  |  | Upgrade compatibility checks validating that a runtime upgrade stays compatible with the policy versions bound to that deployment
WI-050 | M4 | Phase 4 | Validation | L | AIG |  |  |  | One customer-managed deployment validated end to end inside a customer-controlled account: local evaluation, cache behavior during a simulated outage, telemetry configuration, upgrade check
WI-050 | M4 | Phase 4 | Validation | L | OPS |  |  |  | One customer-managed deployment validated end to end inside a customer-controlled account: local evaluation, cache behavior during a simulated outage, telemetry configuration, upgrade check
WI-050 | M4 | Phase 4 | Validation | L | SEC |  |  |  | One customer-managed deployment validated end to end inside a customer-controlled account: local evaluation, cache behavior during a simulated outage, telemetry configuration, upgrade check
WI-050 | M4 | Phase 4 | Validation | L | CONS |  |  |  | One customer-managed deployment validated end to end inside a customer-controlled account: local evaluation, cache behavior during a simulated outage, telemetry configuration, upgrade check
WI-051 | M4 | Phase 4 | Contract | S | AIG |  |  |  | Connector invocation contract verified unchanged between hosted and customer-managed deployments — MVP-09 in shipped form
WI-051 | M4 | Phase 4 | Contract | S | OPS |  |  |  | Connector invocation contract verified unchanged between hosted and customer-managed deployments — MVP-09 in shipped form
WI-051 | M4 | Phase 4 | Contract | S | SEC |  |  |  | Connector invocation contract verified unchanged between hosted and customer-managed deployments — MVP-09 in shipped form
WI-051 | M4 | Phase 4 | Contract | S | CONS |  |  |  | Connector invocation contract verified unchanged between hosted and customer-managed deployments — MVP-09 in shipped form
WI-052 | M5 | Phase 5 | Evaluation | L | AIG |  |  |  | Retrieval-content evaluation available as an evaluator behind the existing adapter pattern, without redesigning the evaluation contract
WI-052 | M5 | Phase 5 | Evaluation | L | OPS |  |  |  | Retrieval-content evaluation available as an evaluator behind the existing adapter pattern, without redesigning the evaluation contract
WI-052 | M5 | Phase 5 | Evaluation | L | SEC |  |  |  | Retrieval-content evaluation available as an evaluator behind the existing adapter pattern, without redesigning the evaluation contract
WI-052 | M5 | Phase 5 | Evaluation | L | CONS |  |  |  | Retrieval-content evaluation available as an evaluator behind the existing adapter pattern, without redesigning the evaluation contract
WI-053 | M5 | Phase 5 | Evaluation | XL | AIG |  |  |  | Indirect prompt-injection detection available as a new evaluator behind the same adapter pattern
WI-053 | M5 | Phase 5 | Evaluation | XL | OPS |  |  |  | Indirect prompt-injection detection available as a new evaluator behind the same adapter pattern
WI-053 | M5 | Phase 5 | Evaluation | XL | SEC |  |  |  | Indirect prompt-injection detection available as a new evaluator behind the same adapter pattern
WI-053 | M5 | Phase 5 | Evaluation | XL | CONS |  |  |  | Indirect prompt-injection detection available as a new evaluator behind the same adapter pattern
WI-054 | M5 | Phase 5 | Evaluation | L | AIG |  |  |  | Tool-call validation using the tool_call evaluation stage
WI-054 | M5 | Phase 5 | Evaluation | L | OPS |  |  |  | Tool-call validation using the tool_call evaluation stage
WI-054 | M5 | Phase 5 | Evaluation | L | SEC |  |  |  | Tool-call validation using the tool_call evaluation stage
WI-054 | M5 | Phase 5 | Evaluation | L | CONS |  |  |  | Tool-call validation using the tool_call evaluation stage
WI-055 | M5 | Phase 5 | Evaluation | L | AIG |  |  |  | Tool-result evaluation using the tool_result evaluation stage
WI-055 | M5 | Phase 5 | Evaluation | L | OPS |  |  |  | Tool-result evaluation using the tool_result evaluation stage
WI-055 | M5 | Phase 5 | Evaluation | L | SEC |  |  |  | Tool-result evaluation using the tool_result evaluation stage
WI-055 | M5 | Phase 5 | Evaluation | L | CONS |  |  |  | Tool-result evaluation using the tool_result evaluation stage
WI-056 | M5 | Phase 5 | Evaluation | L | AIG |  |  |  | Memory-write controls using the memory_write evaluation stage, fitted to the existing Evaluation and Decision entities
WI-056 | M5 | Phase 5 | Evaluation | L | OPS |  |  |  | Memory-write controls using the memory_write evaluation stage, fitted to the existing Evaluation and Decision entities
WI-056 | M5 | Phase 5 | Evaluation | L | SEC |  |  |  | Memory-write controls using the memory_write evaluation stage, fitted to the existing Evaluation and Decision entities
WI-056 | M5 | Phase 5 | Evaluation | L | CONS |  |  |  | Memory-write controls using the memory_write evaluation stage, fitted to the existing Evaluation and Decision entities
WI-057 | M5 | Phase 5 | Control plane | XL | AIG |  |  |  | Human approval workflows for the require_approval decision action, which is reserved in the schema but has no owning workflow before this milestone
WI-057 | M5 | Phase 5 | Control plane | XL | OPS |  |  |  | Human approval workflows for the require_approval decision action, which is reserved in the schema but has no owning workflow before this milestone
WI-057 | M5 | Phase 5 | Control plane | XL | SEC |  |  |  | Human approval workflows for the require_approval decision action, which is reserved in the schema but has no owning workflow before this milestone
WI-057 | M5 | Phase 5 | Control plane | XL | CONS |  |  |  | Human approval workflows for the require_approval decision action, which is reserved in the schema but has no owning workflow before this milestone
WI-058 | M5 | Phase 5 | Evaluation | L | AIG |  |  |  | Agent delegation restrictions
WI-058 | M5 | Phase 5 | Evaluation | L | OPS |  |  |  | Agent delegation restrictions
WI-058 | M5 | Phase 5 | Evaluation | L | SEC |  |  |  | Agent delegation restrictions
WI-058 | M5 | Phase 5 | Evaluation | L | CONS |  |  |  | Agent delegation restrictions
WI-059 | M5 | Phase 5 | Integration | L | AIG |  |  |  | MCP integration scoped narrowly to the platform's own tool-call evaluation, explicitly distinguished from a general-purpose MCP security platform
WI-059 | M5 | Phase 5 | Integration | L | OPS |  |  |  | MCP integration scoped narrowly to the platform's own tool-call evaluation, explicitly distinguished from a general-purpose MCP security platform
WI-059 | M5 | Phase 5 | Integration | L | SEC |  |  |  | MCP integration scoped narrowly to the platform's own tool-call evaluation, explicitly distinguished from a general-purpose MCP security platform
WI-059 | M5 | Phase 5 | Integration | L | CONS |  |  |  | MCP integration scoped narrowly to the platform's own tool-call evaluation, explicitly distinguished from a general-purpose MCP security platform
WI-060 | M5 | Phase 5 | Integration | L | AIG |  |  |  | Advanced authorization integration, without redefining a guardrail decision as a business-authorization decision
WI-060 | M5 | Phase 5 | Integration | L | OPS |  |  |  | Advanced authorization integration, without redefining a guardrail decision as a business-authorization decision
WI-060 | M5 | Phase 5 | Integration | L | SEC |  |  |  | Advanced authorization integration, without redefining a guardrail decision as a business-authorization decision
WI-060 | M5 | Phase 5 | Integration | L | CONS |  |  |  | Advanced authorization integration, without redefining a guardrail decision as a business-authorization decision

## Roadmap
Roadmap
Dependency sequencing, not scheduling. No calendar dates or durations exist in the source material and none are invented here.
Milestone | Name | Phase | Primary deployment mode | Objective | Entry condition
M1 | Integration proof | Phase 1 | Mode A — Remote Evaluation only | Prove that guardrail policy and evaluation can be separated from LiteLLM and reused across multiple gateways. | None — this is the delivery entry point.
M2 | Internal multi-team platform | Phase 2 | Mode A — Remote Evaluation | Allow multiple internal teams to onboard and operate distinct workloads. | M1 complete: contract, policy format, Bedrock adapter, LiteLLM connector, observe mode, basic auditing and internal deployment all verified.
M3 | Guarded gateway | Phase 3 | Mode B — Guarded Gateway | Offer a fully hosted model and guardrail path for teams without their own gateway. | M2 complete — the full Phase 1–2 validation demonstration passed. Phase 3 lies beyond that gate and must not be resourced ahead of it.
M4 | Customer-managed runtime | Phase 4 | Mode C — Customer-Managed Runtime | Support workloads that require local evaluation and content isolation. | M2 complete, including the packaging validation. Does not require M3, though delivery sequencing treats Phase 4 as following Phase 3.
M5 | Advanced agent protection | Phase 5 | All modes — new evaluation stages, not a new deployment mode | Extend guardrail coverage beyond prompt and response evaluation. | M4 complete and validated. A separate product expansion — must not be scheduled or resourced as part of M1–M4 delivery.
The full Phase 1–2 validation demonstration — all nine criteria together, against two genuinely independent deployments — passes at M2, not M1. No subset satisfies the gate.

## Dependencies
Dependencies
What has to be true before the work can proceed, and who owns it. None is confirmed today.
Dependency | Type | Needed for | Owner | Status | Why it gates
AWS account provisioning — non-production and production | Internal | Phase 1 kickoff — all infrastructure work | Platform operations lead | Unconfirmed | Every other technical dependency is provisioned into one of these two accounts. It is the first link in the delivery chain, not one dependency among many.
Amazon Bedrock Guardrails access in target Regions | External | Phase 1 — Bedrock Guardrails adapter | Architecture lead | Unconfirmed | The first managed evaluation engine cannot be integrated or exercised without access in the Regions the runtime will serve.
Stable evaluation contract before connector work | Technical | Phase 1 — LiteLLM connector | Technical lead | Not started | Building the connector against a moving contract forces a matching connector revision on every change — and makes decision consistency across two independent instances unverifiable. Freeze and version the contract before connector work starts, not after.
Consuming-team gateway availability and willingness to install the connector | External | Phase 1–2 — validation demonstration | Integration lead / Delivery lead | Unconfirmed | The demonstration needs two organizationally independent instances. Both their existence and that team's cooperation are outside the delivery team's control.
Security review sign-off | Internal | Any workload's observe-to-enforce promotion; any external onboarding | Security and governance lead | Not yet exercised | No workload leaves observe without it, and the criteria that would satisfy it are themselves undefined today.
KMS and Secrets Manager setup | Technical | Phase 1 — encryption at rest and in transit, runtime credential storage | Platform operations lead / Technical lead | Not started | The runtime, policy storage and audit pipeline cannot be deployed with encryption and credential handling in place without them. Part of Phase 1 environment setup, not a later hardening pass.
CI with dependency and container scanning | Technical | Every build from Phase 1 onward — release-blocking | Technical lead | Not started | Required on every build and re-verified for each new deployment artifact, including the container, chart and template Phase 4 introduces. This one never resolves — it must stay continuously satisfied.
Two sit outside the delivery team entirely: managed engine access in the target Regions, and a second team's willingness to run an independent instance. Neither waits on effort, so no AI-assistance factor touches them.

## Release gates
Release gates
Pass or fail statements with a named owner. The nine validation gates must pass together — a subset does not satisfy the demonstration.
ID | Gate | What passing means | Accountable owner | Milestone
RG-MVP-01 | Two instances, one policy | Two independently deployed instances, each with its own connector installation, bound to the identical policy name and version and verified to resolve the same policy content. | Delivery lead | M1
RG-MVP-02 | No shared provider credentials | Neither instance's model-provider credentials are held, stored or transmitted to the guardrail platform; verified against the platform's own stored secrets. | Security and governance lead | M1
RG-MVP-03 | Consistent normalized decisions | Equivalent content submitted through both instances returns the identical normalized decision schema: action, allowed status, reason codes, policy name and version, evaluator metadata, correlation identifier. | Delivery lead | M1
RG-MVP-04 | Observe-mode workload | One workload's binding is set to observe; evaluations execute and produce decisions with no enforcement applied on the request path. | Delivery lead | M1
RG-MVP-05 | Enforce-mode workload | The other workload's binding is set to enforce or stricter; a violation triggers the corresponding action on the request path. | Delivery lead | M1
RG-MVP-06 | Policy upgrade and rollback | A new immutable version is published and bound, producing a documented behavior change; the binding is then reverted with prior behavior restored, both transitions captured in audit metadata. | Delivery lead | M2
RG-MVP-07 | Raw-content persistence disablement | With retention configured off, no raw content is found in any runtime store, cache or log after evaluation; decision metadata is still persisted. | Security and governance lead | M1
RG-MVP-08 | Configured failure policy honored | With a detector or the Evaluation API forced into a defined failure condition, the configured behavior executes exactly as configured and the path taken is captured in audit. | Delivery lead | M1
RG-MVP-09 | Repackageable for customer-managed deployment | The runtime packages as a deployable artifact suitable for a customer-managed environment while the connector's invocation contract stays unchanged. | Delivery lead | M1
RG-NFR-01 | Availability objective defined and monitored | A documented availability objective for the hosted Evaluation API exists and has been published to pilot workload owners. The figure itself is TBD — this gate requires the objective to exist, not a number to be met. | Platform operations lead | M2
RG-NFR-02 | Evaluation latency measured and accepted | End-to-end evaluation latency is measured continuously per stage and per deployment mode, and accepted by the pilot workload owners. | Platform operations lead | M2
RG-NFR-03 | Audit delivery measured, failure behavior defined | The proportion of evaluations producing a delivered audit record is measured, and the behavior on delivery failure is defined in policy. | Security and governance lead (with Platform operations lead) | M2
RG-SEC-01 | TLS coverage | Every runtime communication path is TLS-protected — application to connector, connector to Evaluation API, runtime to evaluation engines, runtime to control plane. | Security and governance lead | M1
RG-SEC-02 | Identity-based, least-privilege, short-lived authentication | Every platform consumer authenticates with least-privilege, short-lived credentials rather than long-lived static secrets. | Security and governance lead | M2
RG-SEC-03 | No secrets in telemetry | No telemetry payload emitted by the runtime carries secret material — operational metrics, connector-health signals, and customer-selected telemetry alike. | Security and governance lead | M1
RG-SEC-04 | Container and dependency scan clean | Every runtime image and declared dependency in the release is scanned for known vulnerabilities before release. | Security and governance lead | M1
Verification method, environment and sign-off owner per criterion are only partly assigned upstream — a gap owed before the first phase exits.