AI Guardrails — Local-First Delivery Plan

Building the first release with no cloud account, and landing on AWS last

Status: draft for approval. Nothing built or piloted.

Decision requested: approve the build sequence in section 2 and the two records in section 1.

# 1. Executive summary

## What we are building

Teams across the organisation each run their own LLM gateway. Today every team writes its own safety checks, so the same organisational rule is implemented differently in every place it applies, and nobody can say with evidence which rule is in force where.

AI Guardrails makes the safety policy a separate, versioned, reusable thing. A team keeps its own gateway, its own model provider and its own request path, and calls out to a shared evaluation service that answers one question: may this content proceed, and why. The policy, the evaluation and the audited decision are the product. The gateway is not.

| Application | ▶ | Team's own gateway | ▶ | Check the prompt | ▶ | Model | ▶ | Check the response | ▶ | Response |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

The two checks call the shared service. Everything else stays where it already is.

The first release exists to prove one claim: that a single policy can govern two independently operated gateways and produce the same decision in both. If that holds, the approach scales to every team. If it does not, nothing built afterwards matters.

## The constraint: no cloud account

We have no AWS account, and getting one is not on a date we control. The question this plan answers is whether that blocks the work.

It largely does not. The first release depends on twelve platform services. Eleven are infrastructure choices — compute, storage, queues, secrets, metrics — and each has a local stand-in that meets the actual requirement. Policy storage needs immutable versioning, not a specific cloud product. Audit needs a durable append-only record, not a specific queue.

One dependency has no local substitute: Amazon Bedrock Guardrails, the hosted detection engine we intend to buy rather than build. It exists only as a cloud service. That is the honest gap — and a narrower one than it sounds, because detection itself does not wait for it. Four detectors are built and tested locally from the start.

Bottom line. Fourteen of the seventeen capabilities in the first release can be built and demonstrated locally. Three need a cloud account: the managed detection engine, hosted deployment, and multi-region availability. All three are grouped into the final stage.

## What building locally first buys us

No spend and no account dependency until the last stage. Funding confirmation and account provisioning stop gating the start of work.

A later phase gets de-risked for free. Some teams will eventually require the evaluation runtime to sit inside their own network and keep working when it cannot reach our control plane. Building while no control plane exists forces that independence from the first commit, instead of discovering the coupling months later.

Vendor independence is proven, not asserted. We have committed that no detection vendor's data shapes leak into our own contract. Standing up two non-vendor engines first makes that boundary structural rather than a rule someone has to remember.

Failure behaviour gets tested properly. What happens when a detector is down or slow is part of policy, not a hardcoded fallback. Locally that is tested by stopping a container — cheaper and more repeatable than provoking the same conditions against a managed service.

## What building locally first costs us

The first release cannot be signed off before the final stage. The managed detection engine is part of it, and deferring a committed deliverable is a change that must be recorded rather than absorbed quietly.

One proof stays open. Confirming that the managed engine's output maps cleanly onto our own decision format cannot be done without the service. Until then the contract is treated as settled in every respect except engine-neutrality.

Two security controls stay unproven. Encryption at rest and cloud-native workload identity are properties of the target platform. Local substitutes demonstrate the design, not the control. Both are proven in the final stage.

Local performance numbers are indicative only. Measurements taken on developer hardware, with no network hop to a managed detector, rank the checks by cost. They do not set a latency budget.

## The decision requested

| # | Decision | Owner |
| --- | --- | --- |
| 1 | Approve the eight-stage sequence in section 2 as the build order for the first release. | Delivery lead, technical lead |
| 2 | Approve recording two entries in the decision log: that development runs locally, and that the managed detection engine is deferred to the final stage with sign-off conditioned on it. | Product lead, security lead |
| 3 | Set a target date for the cloud account request, so the final stage is not the point at which we discover provisioning takes longer than the build did. | Platform operations lead |
| 4 | Confirm that two separately configured gateways satisfy the reuse proof, and that recruiting two real adopting teams remains a separate open commitment. | Delivery lead |

# 2. Delivery roadmap by stage

The order below is not a preference. The domain model and the evaluation contract have to exist before any gateway integration, because an integration is only a client of that contract. The single change this plan makes is to move every cloud-bound item out of its original position and into the final stage.

| S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Runs entirely on local infrastructure — no account, no spend |  |  |  |  |  |  | Cloud |

| Stage | What it delivers | Cloud |
| --- | --- | --- |
| S0 Foundations | Development environment, service skeletons, container topology, task commands. | No |
| S1 Contract | The six things the system talks about — tenant, workload, policy, binding, evaluation, decision — and the evaluation contract: what a caller sends, and the single normalised decision shape that comes back regardless of which detector produced it. | No |
| S2 Policy model | A versioned, immutable policy format. Changing a policy always creates a new version; nothing is edited in place. Every policy must declare what happens when evaluation fails. | No |
| S3 Runtime | The service that actually evaluates: resolves which policy applies, runs the configured detectors, normalises their output into one decision, records the decision, and measures how long each detector took. | No |
| S4 Integration | The gateway plug-in that calls the service before and after the model, enforces the answer, and reports nothing back that the policy did not ask for. Runs in observe mode: decisions are recorded, nothing is blocked. | No |
| S5 Control plane | Registering a team and a workload, binding a workload to a policy version, promoting it from observe to enforce, and rolling it back instantly. | No |
| S6 Proof | Two independently configured gateways against one policy, and the nine acceptance conditions in section 3 run as an automated suite. | No |
| S7 Cloud landing | Managed detection engine, hosted deployment, encryption and identity controls, regional placement, and the whole proof re-run on real infrastructure. | Yes |

## 2.1 How each cloud dependency is covered until the final stage

‘Met’ means the requirement is genuinely satisfied — for policy storage the requirement is immutable versioning, and a version-controlled repository provides it.

| What is needed | Local stand-in | Status |
| --- | --- | --- |
| Somewhere to run the service | Containers on a developer machine | Met |
| An HTTP surface | Local application server | Met |
| Immutable policy storage | Version-controlled repository | Met |
| A workload and tenant registry | Relational store | Met — the schema is ours |
| A durable audit record | Local queue and append-only archive | Met |
| Secret handling | Encrypted local store | Met for development |
| Latency and decision metrics | Structured logs and histograms | Met |
| Encryption at rest | Deferred | Proven in S7 |
| Workload identity and least-privilege access | Local tokens or a local identity provider | Proven in S7 |
| The bought detection engine | Local detectors carry the load; its adapter is stubbed | Mapping validated in S7 |

## 2.2 The detection-engine gap

Bedrock Guardrails is a hosted service that classifies text against policies you configure — harmful content, prompt attacks, banned topics, personal data. It is the one dependency with no stand-in, because what is being bought is the classifier itself: there is no container to run and no offline edition. It is also, deliberately, the first detection engine and not a permanent one — our own contract has to survive replacing it.

So the detector layer gets built regardless, against engines we do not intend to keep. Four run locally from the first weeks: a rule-based detector, a sensitive-data detector, a structured-output validator, and one called over the network so the remote path is exercised for real. The bought engine sits behind the same interface with recorded responses standing in for the service.

Why this is an advantage, not a workaround. Because the contract never meets the eventual vendor during the entire local build, nothing vendor-shaped can leak into it. Independence becomes structural rather than a rule someone has to keep remembering. What waits for a cloud account is one thing only: confirming this vendor's output maps cleanly onto our decision format.

## 2.3 What this plan does not change

Scope. Reordering work is not a change of scope. Nothing is added, removed or pulled forward.

The acceptance bar. All nine conditions in section 3 still apply, unamended.

Observe before enforce. No workload starts out blocking traffic. Promotion is a deliberate, recorded act.

Later phases. Everything beyond the first release stays behind it.

# 3. Milestones and decision gates

Each stage closes at a gate, passed on evidence rather than on elapsed effort. Dates are deliberately absent: no duration, headcount or delivery date has been agreed yet, and inventing one here would give it a status it has not earned.

| Gate | Passed when | Decided by |
| --- | --- | --- |
| G0 | One command brings the whole stack up locally. | Technical lead |
| G1 | The contract is specified, typed models are generated from it, and the conformance suite is scaffolded. | Architecture lead |
| G2 | Two policy versions exist, both retrievable, neither editable in place, and each declares its behaviour for every way evaluation can fail. | Technical lead, policy owner |
| G3 | An evaluation returns one normalised decision drawn from several detectors; stopping a detector produces the behaviour the policy declared, not an undocumented fallback. | Technical lead |
| G4 | A gateway runs in observe mode with no change to its behaviour, and decisions are being recorded. | Technical lead, integration lead |
| G5 | A workload can be registered, bound, promoted to enforce, and rolled back — with rollback requiring no rebuild of anything. | Product lead, security lead |
| G6 | All nine acceptance conditions pass locally as an automated suite. | Delivery lead |
| G7 | The same suite passes on real infrastructure with the managed engine in place, and the security controls are proven. The first release can be signed off. | Architecture lead, security lead |

## 3.1 Decisions this plan needs, and when

Eight decisions must be made rather than assumed. Local-first work closes two of them earlier than a cloud-first sequence would, and moves four to a single checkpoint at the final stage.

| Decision | Closes at | Note |
| --- | --- | --- |
| What a blocked response returns to the caller | G4 | Brought forward — building the integration forces the question. |
| Which parts of a shared policy a team may override | G5 | Brought forward — the binding model surfaces it. |
| Latency budget and availability target | G6 → G7 | Ranked locally; the figure itself comes from real measurement. |
| Which container platform hosts the service | S7 entry | Genuinely deferrable — the deliverable is a container either way. |
| Target region, and whether the managed engine is fully available there | S7 entry | No local path. |
| Funding commitment | S7 entry | No longer gates the start of the build. |
| Cloud account request filed | S7 entry | Should be filed well before S7 — see the ask in section 1. |
| Two named teams willing to adopt | Unchanged | Local work proves the technical claim; the adoption commitment is separate and stays open. |

## 3.2 The nine acceptance conditions

The first release is accepted only when all nine hold at once — not when the components merely exist. Eight are provable without a cloud account.

| # | Condition | Proven at |
| --- | --- | --- |
| 1 | Two separate gateways run the same policy | G6 |
| 2 | Neither gateway shares its model credentials with the guardrail service | G6 |
| 3 | Both get the same decision for the same content | G6 |
| 4 | One workload runs in observe mode | G4 |
| 5 | Another runs in enforce mode | G5 |
| 6 | A policy can be upgraded and rolled back | G5 |
| 7 | Storing raw prompts and responses can be switched off | G3 |
| 8 | A failed evaluation behaves the way the policy said it would | G3 |
| 9 | The service can later be packaged to run inside a team's own network without changing the integration | G6 |

Worth being precise. The detection-engine gap blocks none of these nine conditions. It blocks one capability and one proof. The demonstration can pass locally; sign-off still waits for the final stage.

# 4. Deliverable plan

Twenty-six tasks, each sized for one software engineer — the plan assumes a single fungible role, so any engineer can pick up any task. Sizes are a deliberate three-step ladder of one, three or five days. They are a sizing judgement, not a bottom-up estimate, and are shown so the shape of the work can be argued with rather than guessed at.

The work falls into three waves. Wave 2 is where the parallelism lives: five tracks that share nothing once the contract exists.

| Wave 1 sequential | ▶ | Wave 2 5 parallel tracks | ▶ | Wave 3 sequential |
| --- | --- | --- | --- | --- |

Waves 1 and 3 are chains — no amount of people makes them shorter.

## 4.1 Wave 1 — foundations (11 days, blocks everything)

| ID | Task | Days |
| --- | --- | --- |
| T1 | Development environment, service skeletons, container topology, task commands | 3 |
| T2 | The six entities and the evaluation contract: what a caller sends, and the one decision shape that comes back | 5 |
| T3 | Typed models generated from the contract; conformance suite scaffolded | 3 |

These three run strictly in order. Nothing else can start until the contract exists, because every other task is a client of it.

## 4.2 Wave 2 — five independent tracks (58 days)

| Track | ID | Task | Days |
| --- | --- | --- | --- |
| A Policy 9 d | T4 | Policy schema: stages, detector configuration, thresholds, outcomes | 3 |
|  | T5 | Immutable versioned store — a change is always a new version | 3 |
|  | T6 | Declared failure behaviour for every way evaluation can fail | 3 |
| B Runtime 12 d | T7 | Policy resolution from a local cache, never a blocking call out | 3 |
|  | T8 | Decision engine — normalise every detector's output into one shape | 5 |
|  | T9 | Audit record and archive, raw content off by default | 3 |
|  | T10 | Timing captured per detector and per stage | 1 |
| C Detectors 13 d | T11 | Rule-based detector for organisation-specific checks | 3 |
|  | T12 | Sensitive-data detector | 3 |
|  | T13 | Structured-output validator | 1 |
|  | T14 | A detector called over the network, exercising timeout and unavailability for real | 3 |
|  | T15 | Managed-engine adapter, stubbed with recorded responses | 3 |
| D Integration 12 d | T16 | Gateway hooks before and after the model call | 5 |
|  | T17 | Enforce the outcome; decide what a blocked response returns | 3 |
|  | T18 | One correlation identifier across both checks; timeout handling | 3 |
|  | T19 | Integration health reporting | 1 |
| E Control plane 12 d | T20 | Tenant and workload registry | 3 |
|  | T21 | Bind a workload to a policy version; promote observe to enforce | 5 |
|  | T22 | Rollback by repointing a binding | 1 |
|  | T23 | Minimal management interface | 3 |

## 4.3 Wave 3 — proof (9 days, sequential)

| ID | Task | Days |
| --- | --- | --- |
| T24 | Two gateways with distinct configurations, model backends, identities and credentials | 3 |
| T25 | The nine acceptance conditions automated as a repeatable suite | 5 |
| T26 | Observe-mode metrics: false-positive rate, latency, spread of decisions | 1 |

## 4.4 What this means for staffing

Seventy-eight engineer-days of work in total. Twenty of them — waves 1 and 3 — are chains that cannot be shortened by adding people. Only wave 2 absorbs extra engineers, and it does so in whole tracks: an engineer takes a track, not a slice of one.

| Engineers | Elapsed | What the extra person buys |
| --- | --- | --- |
| 1 | 78 days | — |
| 2 | 53 days | 25 days. The largest single gain. |
| 3 | 44 days | 9 days. |
| 4 | 41 days | 3 days — one engineer still carries two tracks. |
| 5 | 33 days | 8 days. One engineer per track — the natural size of this plan. |
| 6 or more | 33 days | Nothing. Wave 1, the longest track and wave 3 set the floor. |

The decision in one line. Five engineers is the natural team for this plan and finishes in about a third of the elapsed time one engineer would need. A sixth adds nothing. Two engineers is the best value per head if capacity is scarce.

One caution on the model: it assumes a clean barrier between waves, so no track starts before the contract is finished and nothing in wave 3 starts before every track is done. Real delivery overlaps at the edges, which would shorten every figure above. Treat these as the conservative end.